## orders
order_id | client | product_type | quantity | start_date | deadline | assigned_lab | assigned_chain | progress_percentage | priority
ORD-0001 | Atelier Roma | Giacca | 120 | 2026-05-25 | 2026-06-08 | L1 | Chain-A | 0 | normal
ORD-0002 | Boutique Milano | Pantalone | 200 | 2026-05-25 | 2026-06-04 | L1 | Chain-A | 0.1 | normal
ORD-0003 | Studio Firenze | Giacca | 600 | 2026-05-25 | 2026-06-06 | L2 | Chain-B | 0 | normal
ORD-0004 | House Torino | Pantalone | 80 | 2026-05-27 | 2026-06-14 | L2 | Chain-B | 0 | low
ORD-0005 | Maison Venezia | Giacca | 150 | 2026-05-25 | 2026-05-29 | L1 | Chain-A | 0 | urgent

## product_matrix
product_type | phase_name | min_time_minutes | max_time_minutes | avg_time_minutes | setup_time_minutes | phase_order
Giacca | imbastitura | 8 | 12 | 10 | 2 | 1
Giacca | rifilo | 4 | 6 | 5 | 1 | 2
Giacca | confezione capo | 15 | 22 | 18 | 3 | 3
Giacca | controllo misure | 2 | 4 | 3 | 0.5 | 4
Pantalone | imbastitura | 5 | 9 | 7 | 1.5 | 1
Pantalone | rifilo | 3 | 5 | 4 | 1 | 2
Pantalone | confezione capo | 10 | 16 | 13 | 2.5 | 3
Pantalone | controllo misure | 2 | 3 | 2.5 | 0.5 | 4

## labs
lab_id | lab_name | working_hours_per_day | working_days_per_week | default_efficiency | machine_uptime | max_weekly_hours | overtime_allowed
L1 | Laboratorio Nord | 8 | 5 | 0.8 | 0.92 | 48 | FALSE
L2 | Laboratorio Sud | 8 | 5 | 0.75 | 0.88 | 48 | FALSE

## phase_capacity
lab_id | phase_name | workers_total | workers_assigned | machines_total | available_minutes_per_day | efficiency | uptime
L1 | imbastitura | 4 | 4 | 2 | 1413.12 | 0.8 | 0.92
L1 | rifilo | 3 | 3 | 2 | 1059.84 | 0.8 | 0.92
L1 | confezione capo | 6 | 5 | 4 | 1766.4 | 0.8 | 0.92
L1 | controllo misure | 2 | 2 | 0 | 706.56 | 0.8 | 0.92
L2 | imbastitura | 3 | 3 | 2 | 950.4 | 0.75 | 0.88
L2 | rifilo | 2 | 2 | 1 | 633.6 | 0.75 | 0.88
L2 | confezione capo | 4 | 4 | 3 | 1267.2 | 0.75 | 0.88
L2 | controllo misure | 2 | 1 | 0 | 316.8 | 0.75 | 0.88