## Dashboard
Clothing Production Planning Database
Last refreshed | 46169
Input source | sample_planning test 2.xlsx + cleaned planning database
KPI | Value
Total orders | 60
Total units | 20600
Average progress | 0.441
High/overdue risk orders | 0
Open TNA milestones | 231
Potential phase bottlenecks | 127
Risk level | Order count
LOW | 60
MEDIUM | 0
HIGH | 0
OVERDUE | 0
Product type | Order count | Units
Cappotto | 6 | 1710
Gonna | 4 | 1190
Camicia | 3 | 1320
Abito | 5 | 910
Jeans | 10 | 3250
T-shirt | 4 | 1450
Pantalone | 3 | 1440
Blazer | 4 | 1140
Felpa | 1 | 300
Top | 5 | 1520
Kimono | 3 | 1190
Body | 3 | 1420

## style_master
style_id | style_name | product_type | category | material_family | size_range | complexity_score | estimated_smv | tech_pack_status
STY-001-1 | Cappotto Navy | Cappotto | Outerwear | wool blend | 34-44 | 5 | 85 | Needs update
STY-001-2 | Cappotto Chocolate | Cappotto | Outerwear | wool blend | 1-5 | 5 | 89 | Needs update
STY-002-1 | Gonna Chocolate | Gonna | Bottoms | viscose twill | IT38-IT48 | 2 | 22 | Draft
STY-002-2 | Gonna Sage | Gonna | Bottoms | viscose twill | XS-XL | 2 | 24 | Draft
STY-003-1 | Camicia Sage | Camicia | Tops/Dresses | organic cotton poplin | XS-XL | 3 | 34 | Needs update
STY-003-2 | Camicia Burgundy | Camicia | Tops/Dresses | organic cotton poplin | IT38-IT48 | 3 | 36 | Approved
STY-004-1 | Abito Burgundy | Abito | Tops/Dresses | tencel satin | 36-46 | 4 | 48 | Needs update
STY-004-2 | Abito Powder Blue | Abito | Tops/Dresses | tencel satin | S-XXL | 4 | 50 | Needs update
STY-005-1 | Jeans Powder Blue | Jeans | Bottoms | organic denim | IT38-IT48 | 4 | 41 | Draft
STY-005-2 | Jeans Charcoal | Jeans | Bottoms | organic denim | 36-46 | 4 | 43 | Draft
STY-006-1 | T-shirt Charcoal | T-shirt | Tops/Dresses | organic cotton jersey | 1-5 | 1 | 18 | Needs update
STY-006-2 | T-shirt Sand | T-shirt | Tops/Dresses | organic cotton jersey | S-XXL | 1 | 21 | Approved
STY-007-1 | Pantalone Sand | Pantalone | Bottoms | recycled wool suiting | S-XXL | 3 | 37 | Needs update
STY-007-2 | Pantalone Olive | Pantalone | Bottoms | recycled wool suiting | S-XXL | 3 | 40 | Approved
STY-008-1 | Blazer Olive | Blazer | Outerwear | wool suiting | 36-46 | 5 | 70 | Approved
STY-008-2 | Blazer Off White | Blazer | Outerwear | wool suiting | XS-XL | 5 | 72 | Draft
STY-009-1 | Felpa Off White | Felpa | Tops/Dresses | organic cotton fleece | 34-44 | 2 | 27 | Needs update
STY-009-2 | Felpa Rose | Felpa | Tops/Dresses | organic cotton fleece | IT38-IT48 | 2 | 31 | Needs update
STY-010-1 | Top Rose | Top | Tops/Dresses | bamboo jersey | 1-5 | 1 | 14 | Draft
STY-010-2 | Top Black | Top | Tops/Dresses | bamboo jersey | 34-44 | 1 | 18 | Approved
STY-011-1 | Kimono Black | Kimono | Tops/Dresses | peace silk | 34-44 | 3 | 42 | Draft
STY-011-2 | Kimono Ivory | Kimono | Tops/Dresses | peace silk | 70B-90D | 3 | 45 | Draft
STY-012-1 | Body Ivory | Body | Underwear | modal stretch | 36-46 | 3 | 31 | Draft
STY-012-2 | Body Navy | Body | Underwear | modal stretch | 34-44 | 3 | 32 | Needs update
STY-013-1 | Slip Navy | Slip | Underwear | organic cotton rib | S-XXL | 1 | 12 | Approved
STY-013-2 | Slip Chocolate | Slip | Underwear | organic cotton rib | S-XXL | 1 | 13 | Approved
STY-014-1 | Bra Chocolate | Bra | Underwear | tencel mesh | IT38-IT48 | 5 | 38 | Draft
STY-014-2 | Bra Sage | Bra | Underwear | tencel mesh | 1-5 | 5 | 40 | Needs update
STY-015-1 | Boxer Sage | Boxer | Underwear | organic cotton poplin | 34-44 | 1 | 16 | Approved
STY-015-2 | Boxer Burgundy | Boxer | Underwear | organic cotton poplin | 1-5 | 1 | 17 | Needs update
STY-016-1 | Baby doll Burgundy | Baby doll | Underwear | tencel satin | 36-46 | 4 | 36 | Needs update
STY-016-2 | Baby doll Powder Blue | Baby doll | Underwear | tencel satin | S-XXL | 4 | 39 | Approved

## orders
order_id | client | style_id | product_type | quantity | size_range | start_date | deadline | ex_factory_date | assigned_lab | assigned_line | priority | status | progress_percentage | planned_smv | total_standard_minutes | capacity_days_needed | days_to_deadline | on_time_risk
ORD-1010 | Sartoria Napoli | STY-001-2 | Cappotto | 180 | 1-5 | 2026-06-01 | 2026-06-18 | 2026-06-16 | L3 | LN-011 | normal | materials pending | 5% | 89 | 16020 | 9.0447 | 22 | LOW
ORD-1011 | Atelier Bologna | STY-002-1 | Gonna | 240 | IT38-IT48 | 2026-06-01 | 2026-06-13 | 2026-06-11 | L3 | LN-011 | high | shipped | 0% | 22 | 5280 | 2.981 | 17 | LOW
ORD-1012 | Boutique Genova | STY-003-2 | Camicia | 500 | IT38-IT48 | 2026-06-02 | 2026-06-21 | 2026-06-19 | L4 | LN-016 | normal | ready to ship | 12% | 36 | 18000 | 7.717 | 25 | LOW
ORD-1013 | Moda Verona | STY-004-2 | Abito | 150 | S-XXL | 2026-06-03 | 2026-06-11 | 2026-06-09 | L3 | LN-011 | urgent | not started | 0% | 50 | 7500 | 4.2344 | 15 | LOW
ORD-1014 | Casa Palermo | STY-005-1 | Jeans | 320 | IT38-IT48 | 2026-06-01 | 2026-06-16 | 2026-06-14 | L4 | LN-016 | normal | shipped | 3% | 41 | 13120 | 5.6248 | 20 | LOW
ORD-1106 | Sartoria Napoli | STY-012-2 | Body | 300 | 34-44 | 2026-07-06 | 2026-07-30 | 2026-07-28 | L8 | LN-035 | normal | not started | 63% | 32 | 9600 | 2.6833 | 64 | LOW
ORD-1107 | Atelier Bologna | STY-005-1 | Jeans | 1000 | IT38-IT48 | 2026-08-10 | 2026-09-04 | 2026-08-29 | L4 | LN-016 | normal | not started | 31% | 41 | 41000 | 17.5776 | 100 | LOW
ORD-1108 | Boutique Genova | STY-005-2 | Jeans | 120 | 36-46 | 2026-08-24 | 2026-09-06 | 2026-09-03 | L1 | LN-002 | normal | quality control | 75% | 43 | 5160 | 2.7821 | 102 | LOW
ORD-1109 | Venezia Atelier | STY-005-2 | Jeans | 120 | 36-46 | 2026-09-04 | 2026-09-20 | 2026-09-15 | L8 | LN-035 | normal | shipped | 49% | 43 | 5160 | 1.4423 | 116 | LOW
ORD-1110 | Linea Roma | STY-002-2 | Gonna | 650 | XS-XL | 2026-06-04 | 2026-06-19 | 2026-06-14 | L7 | LN-030 | high | shipped | 65% | 24 | 15600 | 2.9762 | 23 | LOW
ORD-1111 | Boutique Genova | STY-005-1 | Jeans | 220 | IT38-IT48 | 2026-08-19 | 2026-10-10 | 2026-10-04 | L9 | LN-039 | normal | shipped | 36% | 41 | 9020 | 1.2125 | 136 | LOW
ORD-1112 | Studio Firenze | STY-004-1 | Abito | 320 | 36-46 | 2026-06-30 | 2026-08-07 | 2026-08-03 | L8 | LN-035 | high | quality control | 40% | 48 | 15360 | 4.2932 | 72 | LOW
ORD-1113 | Bari Concept | STY-012-1 | Body | 320 | 36-46 | 2026-06-09 | 2026-06-26 | 2026-06-24 | L2 | LN-007 | high | cutting | 9% | 31 | 9920 | 4.7249 | 30 | LOW
ORD-1114 | Studio Firenze | STY-011-1 | Kimono | 240 | 34-44 | 2026-08-25 | 2026-10-03 | 2026-09-26 | L1 | LN-002 | normal | materials pending | 57% | 42 | 10080 | 5.4348 | 129 | LOW
ORD-1115 | Bari Concept | STY-007-1 | Pantalone | 320 | S-XXL | 2026-06-29 | 2026-07-17 | 2026-07-13 | L9 | LN-039 | normal | sewing | 11% | 37 | 11840 | 1.5916 | 51 | LOW
ORD-1116 | Sartoria Napoli | STY-001-2 | Cappotto | 150 | 1-5 | 2026-07-05 | 2026-08-05 | 2026-08-01 | L6 | LN-026 | normal | ready to ship | 17% | 89 | 13350 | 5.258 | 70 | LOW
ORD-1117 | Cagliari Studio | STY-001-1 | Cappotto | 400 | 34-44 | 2026-06-28 | 2026-08-03 | 2026-07-29 | L8 | LN-035 | normal | quality control | 15% | 85 | 34000 | 9.5032 | 68 | LOW
ORD-1118 | Torino Mode | STY-005-1 | Jeans | 80 | IT38-IT48 | 2026-08-26 | 2026-09-12 | 2026-09-08 | L8 | LN-035 | high | ready to ship | 46% | 41 | 3280 | 0.91678 | 108 | LOW
ORD-1119 | Studio Firenze | STY-004-2 | Abito | 120 | S-XXL | 2026-07-07 | 2026-08-31 | 2026-08-24 | L10 | LN-044 | high | not started | 50% | 50 | 6000 | 1.0458 | 96 | LOW
ORD-1120 | Moda Verona | STY-002-1 | Gonna | 220 | IT38-IT48 | 2026-06-28 | 2026-07-18 | 2026-07-14 | L5 | LN-021 | normal | ready to ship | 11% | 22 | 4840 | 2.4174 | 52 | LOW
ORD-1121 | Atelier Bologna | STY-008-2 | Blazer | 300 | XS-XL | 2026-09-03 | 2026-09-17 | 2026-09-12 | L1 | LN-002 | high | ready to ship | 88% | 72 | 21600 | 11.646 | 113 | LOW
ORD-1122 | Atelier Bologna | STY-014-2 | Bra | 300 | 1-5 | 2026-06-03 | 2026-07-05 | 2026-07-02 | L10 | LN-044 | high | materials pending | 79% | 40 | 12000 | 2.0916 | 39 | LOW
ORD-1123 | Torino Mode | STY-008-2 | Blazer | 300 | XS-XL | 2026-08-07 | 2026-08-24 | 2026-08-19 | L5 | LN-021 | normal | materials pending | 21% | 72 | 21600 | 10.7883 | 89 | LOW
ORD-1124 | Maison Milano | STY-004-1 | Abito | 240 | 36-46 | 2026-09-02 | 2026-10-25 | 2026-10-22 | L4 | LN-016 | normal | cutting | 14% | 48 | 11520 | 4.9389 | 151 | LOW
ORD-1125 | Bari Concept | STY-003-1 | Camicia | 320 | XS-XL | 2026-07-30 | 2026-09-16 | 2026-09-10 | L8 | LN-035 | urgent | quality control | 61% | 34 | 10880 | 3.041 | 112 | LOW
ORD-1126 | Casa Palermo | STY-015-2 | Boxer | 500 | 1-5 | 2026-06-08 | 2026-07-12 | 2026-07-06 | L2 | LN-007 | normal | not started | 44% | 17 | 8500 | 4.0485 | 46 | LOW
ORD-1127 | Torino Mode | STY-003-1 | Camicia | 500 | XS-XL | 2026-08-04 | 2026-09-09 | 2026-09-04 | L10 | LN-044 | urgent | shipped | 91% | 34 | 17000 | 2.9631 | 105 | LOW
ORD-1128 | Sartoria Napoli | STY-016-1 | Baby doll | 320 | 36-46 | 2026-06-14 | 2026-07-17 | 2026-07-10 | L2 | LN-007 | urgent | sewing | 61% | 36 | 11520 | 5.487 | 51 | LOW
ORD-1129 | Maison Milano | STY-015-1 | Boxer | 240 | 34-44 | 2026-07-07 | 2026-08-12 | 2026-08-07 | L6 | LN-026 | urgent | materials pending | 5% | 16 | 3840 | 1.5124 | 77 | LOW
ORD-1130 | Casa Palermo | STY-013-2 | Slip | 800 | S-XXL | 2026-08-24 | 2026-10-13 | 2026-10-10 | L6 | LN-026 | normal | quality control | 55% | 13 | 10400 | 4.0961 | 139 | LOW
ORD-1131 | Torino Mode | STY-013-1 | Slip | 800 | S-XXL | 2026-06-11 | 2026-07-12 | 2026-07-06 | L7 | LN-030 | normal | ready to ship | 77% | 12 | 9600 | 1.8315 | 46 | LOW
ORD-1132 | Moda Verona | STY-010-1 | Top | 240 | 1-5 | 2026-08-02 | 2026-08-26 | 2026-08-23 | L3 | LN-011 | normal | not started | 7% | 14 | 3360 | 1.897 | 91 | LOW
ORD-1133 | Boutique Genova | STY-005-2 | Jeans | 150 | 36-46 | 2026-06-24 | 2026-08-14 | 2026-08-11 | L8 | LN-035 | normal | shipped | 39% | 43 | 6450 | 1.8028 | 79 | LOW
ORD-1134 | Venezia Atelier | STY-015-1 | Boxer | 180 | 34-44 | 2026-07-10 | 2026-08-21 | 2026-08-18 | L6 | LN-026 | urgent | shipped | 94% | 16 | 2880 | 1.1343 | 86 | LOW
ORD-1135 | Torino Mode | STY-006-1 | T-shirt | 150 | 1-5 | 2026-07-03 | 2026-07-18 | 2026-07-11 | L8 | LN-035 | normal | materials pending | 53% | 18 | 2700 | 0.75467 | 52 | LOW
ORD-1136 | Linea Roma | STY-006-2 | T-shirt | 400 | S-XXL | 2026-06-19 | 2026-07-28 | 2026-07-26 | L4 | LN-016 | high | ready to ship | 84% | 21 | 8400 | 3.6013 | 62 | LOW
ORD-1137 | Atelier Bologna | STY-008-2 | Blazer | 240 | XS-XL | 2026-06-29 | 2026-07-12 | 2026-07-08 | L2 | LN-007 | normal | not started | 75% | 72 | 17280 | 8.2305 | 46 | LOW
ORD-1138 | Linea Roma | STY-005-2 | Jeans | 500 | 36-46 | 2026-06-01 | 2026-06-18 | 2026-06-16 | L5 | LN-021 | normal | materials pending | 79% | 43 | 21500 | 10.7383 | 22 | LOW
ORD-1139 | Sartoria Napoli | STY-010-1 | Top | 180 | 1-5 | 2026-07-24 | 2026-09-14 | 2026-09-08 | L8 | LN-035 | normal | not started | 11% | 14 | 2520 | 0.70436 | 110 | LOW
ORD-1140 | Casa Palermo | STY-008-1 | Blazer | 300 | 36-46 | 2026-06-01 | 2026-07-22 | 2026-07-18 | L4 | LN-016 | urgent | quality control | 40% | 70 | 21000 | 9.0032 | 56 | LOW
ORD-1141 | Linea Roma | STY-001-2 | Cappotto | 80 | 1-5 | 2026-08-21 | 2026-09-26 | 2026-09-22 | L5 | LN-021 | normal | quality control | 34% | 89 | 7120 | 3.5561 | 122 | LOW
ORD-1142 | Boutique Genova | STY-004-2 | Abito | 80 | S-XXL | 2026-07-16 | 2026-08-31 | 2026-08-27 | L3 | LN-011 | high | ready to ship | 93% | 50 | 4000 | 2.2584 | 96 | LOW
ORD-1143 | Moda Verona | STY-002-2 | Gonna | 80 | XS-XL | 2026-06-26 | 2026-07-10 | 2026-07-06 | L5 | LN-021 | urgent | finishing | 38% | 24 | 1920 | 0.95896 | 44 | LOW
ORD-1144 | Maison Milano | STY-007-2 | Pantalone | 1000 | S-XXL | 2026-06-07 | 2026-07-30 | 2026-07-26 | L5 | LN-021 | normal | ready to ship | 76% | 40 | 40000 | 19.9783 | 64 | LOW
ORD-1145 | Linea Roma | STY-011-1 | Kimono | 800 | 34-44 | 2026-08-03 | 2026-09-07 | 2026-09-01 | L5 | LN-021 | normal | ready to ship | 69% | 42 | 33600 | 16.7817 | 103 | LOW
ORD-1146 | Atelier Bologna | STY-010-2 | Top | 120 | 34-44 | 2026-07-12 | 2026-09-04 | 2026-08-31 | L5 | LN-021 | high | cutting | 57% | 18 | 2160 | 1.0788 | 100 | LOW
ORD-1147 | Sartoria Napoli | STY-012-2 | Body | 800 | 34-44 | 2026-07-16 | 2026-09-05 | 2026-08-31 | L5 | LN-021 | normal | quality control | 7% | 32 | 25600 | 12.7861 | 101 | LOW
ORD-1148 | Boutique Genova | STY-006-1 | T-shirt | 500 | 1-5 | 2026-08-26 | 2026-10-05 | 2026-10-03 | L3 | LN-011 | normal | quality control | 22% | 18 | 9000 | 5.0813 | 131 | LOW
ORD-1149 | Maison Milano | STY-005-2 | Jeans | 240 | 36-46 | 2026-07-27 | 2026-08-12 | 2026-08-06 | L3 | LN-011 | urgent | finishing | 35% | 43 | 10320 | 5.8266 | 77 | LOW
ORD-1150 | Linea Roma | STY-001-1 | Cappotto | 400 | 34-44 | 2026-07-20 | 2026-09-05 | 2026-09-03 | L5 | LN-021 | normal | finishing | 67% | 85 | 34000 | 16.9815 | 101 | LOW
ORD-1151 | Boutique Genova | STY-007-1 | Pantalone | 120 | S-XXL | 2026-07-28 | 2026-08-20 | 2026-08-13 | L8 | LN-035 | normal | quality control | 77% | 37 | 4440 | 1.241 | 85 | LOW
ORD-1152 | Boutique Genova | STY-010-2 | Top | 800 | 34-44 | 2026-08-30 | 2026-10-21 | 2026-10-18 | L6 | LN-026 | urgent | cutting | 21% | 18 | 14400 | 5.6715 | 147 | LOW
ORD-1153 | Venezia Atelier | STY-001-2 | Cappotto | 500 | 1-5 | 2026-07-18 | 2026-08-28 | 2026-08-22 | L3 | LN-011 | urgent | finishing | 84% | 89 | 44500 | 25.1242 | 93 | LOW
ORD-1154 | Studio Firenze | STY-016-2 | Baby doll | 500 | S-XXL | 2026-06-10 | 2026-06-30 | 2026-06-26 | L2 | LN-007 | high | cutting | 44% | 39 | 19500 | 9.2878 | 34 | LOW
ORD-1155 | Studio Firenze | STY-006-1 | T-shirt | 400 | 1-5 | 2026-06-08 | 2026-06-27 | 2026-06-21 | L3 | LN-011 | normal | sewing | 16% | 18 | 7200 | 4.065 | 31 | LOW
ORD-1156 | Casa Palermo | STY-010-1 | Top | 180 | 1-5 | 2026-08-21 | 2026-10-07 | 2026-10-03 | L3 | LN-011 | normal | cutting | 58% | 14 | 2520 | 1.4228 | 133 | LOW
ORD-1157 | Bari Concept | STY-005-1 | Jeans | 500 | IT38-IT48 | 2026-09-01 | 2026-10-21 | 2026-10-17 | L10 | LN-044 | normal | materials pending | 78% | 41 | 20500 | 3.5731 | 147 | LOW
ORD-1158 | Torino Mode | STY-009-1 | Felpa | 300 | 34-44 | 2026-08-19 | 2026-10-10 | 2026-10-08 | L8 | LN-035 | urgent | shipped | 28% | 27 | 8100 | 2.264 | 136 | LOW
ORD-1159 | Linea Roma | STY-013-2 | Slip | 120 | S-XXL | 2026-08-28 | 2026-09-12 | 2026-09-09 | L8 | LN-035 | high | quality control | 46% | 13 | 1560 | 0.43603 | 108 | LOW
ORD-1160 | Studio Firenze | STY-011-2 | Kimono | 150 | 70B-90D | 2026-07-18 | 2026-08-31 | 2026-08-25 | L2 | LN-007 | normal | finishing | 23% | 45 | 6750 | 3.215 | 96 | LOW
Formulas:
days_to_deadline = [deadline]-TODAY()

## product_matrix
product_type | phase_name | line_type | min_time_minutes | max_time_minutes | avg_time_minutes | setup_time_minutes | phase_order | dependency
Cappotto | taglio tessuto | cutting | 10 | 14 | 12 | 3 | 1 | tech pack approved
Cappotto | adesivazione | cutting | 7 | 11 | 9 | 2 | 2 | previous phase
Cappotto | imbastitura | sewing | 10 | 16 | 13 | 2 | 3 | previous phase
Cappotto | confezione capo | sewing | 28 | 40 | 34 | 5 | 4 | previous phase
Cappotto | applicazione fodera | sewing | 14 | 21 | 18 | 3 | 5 | previous phase
Cappotto | stiro intermedio | finishing | 5 | 8 | 6 | 1 | 6 | previous phase
Cappotto | controllo qualità | quality_control | 4 | 7 | 5 | 0.5 | 7 | previous phase
Cappotto | packing | finishing | 3 | 5 | 4 | 0.5 | 8 | previous phase
Gonna | taglio tessuto | cutting | 5 | 9 | 7 | 2 | 1 | tech pack approved
Gonna | applicazione zip | sewing | 5 | 8 | 6 | 1 | 2 | previous phase
Gonna | confezione capo | sewing | 12 | 18 | 15 | 3 | 3 | previous phase
Gonna | orlo | sewing | 4 | 7 | 5 | 1 | 4 | previous phase
Gonna | stiro finale | finishing | 3 | 5 | 4 | 0.5 | 5 | previous phase
Gonna | controllo qualità | quality_control | 2 | 4 | 3 | 0.5 | 6 | previous phase
Camicia | taglio tessuto | cutting | 6 | 10 | 8 | 2 | 1 | tech pack approved
Camicia | collo e polsi | sewing | 7 | 11 | 9 | 2 | 2 | previous phase
Camicia | asolatura/bottoni | sewing | 4 | 7 | 5 | 1 | 3 | previous phase
Camicia | confezione capo | sewing | 12 | 18 | 15 | 3 | 4 | previous phase
Camicia | stiro finale | finishing | 4 | 6 | 5 | 0.5 | 5 | previous phase
Camicia | controllo qualità | quality_control | 2 | 4 | 3 | 0.5 | 6 | previous phase
Abito | taglio tessuto | cutting | 7 | 12 | 10 | 3 | 1 | tech pack approved
Abito | imbastitura | sewing | 8 | 13 | 11 | 2 | 2 | previous phase
Abito | confezione corpino | sewing | 14 | 22 | 18 | 3 | 3 | previous phase
Abito | confezione gonna | sewing | 10 | 17 | 13 | 3 | 4 | previous phase
Abito | stiro finale | finishing | 4 | 7 | 5 | 1 | 5 | previous phase
Abito | controllo qualità | quality_control | 3 | 5 | 4 | 0.5 | 6 | previous phase
Jeans | taglio tessuto | cutting | 5 | 9 | 7 | 2 | 1 | tech pack approved
Jeans | cuciture tasche | sewing | 8 | 12 | 10 | 2 | 2 | previous phase
Jeans | confezione capo | sewing | 14 | 22 | 18 | 3 | 3 | previous phase
Jeans | lavaggio/trattamenti | washing | 6 | 10 | 8 | 1 | 4 | previous phase
Jeans | stiro finale | finishing | 3 | 5 | 4 | 0.5 | 5 | previous phase
Jeans | controllo qualità | quality_control | 3 | 5 | 4 | 0.5 | 6 | previous phase
T-shirt | taglio tessuto | cutting | 3 | 6 | 4 | 1 | 1 | tech pack approved
T-shirt | spalle e fianchi | sewing | 5 | 8 | 6 | 1 | 2 | previous phase
T-shirt | collo | sewing | 3 | 5 | 4 | 0.5 | 3 | previous phase
T-shirt | orlo | sewing | 3 | 5 | 4 | 0.5 | 4 | previous phase
T-shirt | stiro/packing | finishing | 2 | 4 | 3 | 0.5 | 5 | previous phase
T-shirt | controllo qualità | quality_control | 2 | 3 | 2 | 0.5 | 6 | previous phase
Pantalone | taglio tessuto | cutting | 6 | 10 | 8 | 2 | 1 | tech pack approved
Pantalone | tasche | sewing | 6 | 10 | 8 | 2 | 2 | previous phase
Pantalone | cintura | sewing | 5 | 8 | 6 | 1 | 3 | previous phase
Pantalone | confezione capo | sewing | 12 | 18 | 15 | 3 | 4 | previous phase
Pantalone | stiro finale | finishing | 3 | 5 | 4 | 0.5 | 5 | previous phase
Pantalone | controllo qualità | quality_control | 2 | 4 | 3 | 0.5 | 6 | previous phase
Blazer | taglio tessuto | cutting | 9 | 14 | 11 | 3 | 1 | tech pack approved
Blazer | adesivazione | cutting | 7 | 11 | 9 | 2 | 2 | previous phase
Blazer | costruzione davanti | sewing | 16 | 24 | 20 | 3 | 3 | previous phase
Blazer | maniche | sewing | 12 | 18 | 15 | 3 | 4 | previous phase
Blazer | applicazione fodera | sewing | 12 | 20 | 16 | 3 | 5 | previous phase
Blazer | stiro finale | finishing | 6 | 10 | 8 | 1 | 6 | previous phase
Blazer | controllo qualità | quality_control | 4 | 7 | 5 | 0.5 | 7 | previous phase
Felpa | taglio tessuto | cutting | 4 | 7 | 5 | 1 | 1 | tech pack approved
Felpa | assemblaggio busto | sewing | 7 | 10 | 8 | 1 | 2 | previous phase
Felpa | cappuccio/collo | sewing | 5 | 8 | 6 | 1 | 3 | previous phase
Felpa | polsi e fondo | sewing | 4 | 6 | 5 | 0.5 | 4 | previous phase
Felpa | stiro/packing | finishing | 2 | 4 | 3 | 0.5 | 5 | previous phase
Felpa | controllo qualità | quality_control | 2 | 3 | 2 | 0.5 | 6 | previous phase
Top | taglio tessuto | cutting | 3 | 5 | 4 | 1 | 1 | tech pack approved
Top | confezione capo | sewing | 7 | 10 | 8 | 1 | 2 | previous phase
Top | elastici/finizioni | sewing | 2 | 4 | 3 | 0.5 | 3 | previous phase
Top | stiro finale | finishing | 2 | 3 | 2.5 | 0.5 | 4 | previous phase
Top | controllo qualità | quality_control | 1 | 3 | 2 | 0.5 | 5 | previous phase
Kimono | taglio tessuto | cutting | 7 | 12 | 9 | 2 | 1 | tech pack approved
Kimono | cuciture spalle | sewing | 6 | 10 | 8 | 1 | 2 | previous phase
Kimono | maniche | sewing | 8 | 13 | 10 | 2 | 3 | previous phase
Kimono | cintura | sewing | 4 | 7 | 5 | 1 | 4 | previous phase
Kimono | stiro finale | finishing | 4 | 6 | 5 | 0.5 | 5 | previous phase
Kimono | controllo qualità | quality_control | 2 | 4 | 3 | 0.5 | 6 | previous phase
Body | taglio tessuto | cutting | 4 | 7 | 5 | 1 | 1 | tech pack approved
Body | assemblaggio | sewing | 10 | 15 | 12 | 2 | 2 | previous phase
Body | applicazione elastici | sewing | 6 | 10 | 8 | 1 | 3 | previous phase
Body | bottoni automatici | sewing | 3 | 5 | 4 | 0.5 | 4 | previous phase
Body | controllo qualità | quality_control | 2 | 3 | 2.5 | 0.5 | 5 | previous phase
Slip | taglio tessuto | cutting | 2 | 4 | 3 | 0.5 | 1 | tech pack approved
Slip | assemblaggio | sewing | 5 | 8 | 6 | 0.5 | 2 | previous phase
Slip | elastici | sewing | 3 | 5 | 4 | 0.5 | 3 | previous phase
Slip | controllo qualità | quality_control | 1 | 2 | 1.5 | 0.5 | 4 | previous phase
Bra | taglio tessuto | cutting | 4 | 7 | 5 | 1 | 1 | tech pack approved
Bra | coppe | sewing | 8 | 13 | 10 | 2 | 2 | previous phase
Bra | elastici e spalline | sewing | 7 | 12 | 9 | 1 | 3 | previous phase
Bra | ganci e rifiniture | sewing | 5 | 8 | 6 | 0.5 | 4 | previous phase
Bra | controllo qualità | quality_control | 3 | 5 | 4 | 0.5 | 5 | previous phase
Boxer | taglio tessuto | cutting | 3 | 5 | 4 | 1 | 1 | tech pack approved
Boxer | assemblaggio | sewing | 6 | 10 | 8 | 1 | 2 | previous phase
Boxer | elastico vita | sewing | 3 | 5 | 4 | 0.5 | 3 | previous phase
Boxer | controllo qualità | quality_control | 1 | 3 | 2 | 0.5 | 4 | previous phase
Baby doll | taglio tessuto | cutting | 5 | 8 | 6 | 1 | 1 | tech pack approved
Baby doll | confezione corpino | sewing | 9 | 14 | 11 | 2 | 2 | previous phase
Baby doll | orlo e rifiniture | sewing | 5 | 8 | 6 | 1 | 3 | previous phase
Baby doll | stiro finale | finishing | 2 | 4 | 3 | 0.5 | 4 | previous phase
Baby doll | controllo qualità | quality_control | 2 | 4 | 3 | 0.5 | 5 | previous phase

## labs_factories
lab_id | lab_name | region | city | number_of_workers | working_hours_per_day | working_days_per_week | default_efficiency | machine_uptime | max_weekly_hours | overtime_allowed | risk_level
L1 | Laboratorio Nord | Lombardy | Bergamo | 55 | 8 | 5 | 84% | 92% | 48 | No | Low
L2 | Laboratorio Veneto | Veneto | Vicenza | 80 | 8 | 5 | 81% | 90% | 48 | Yes | Medium
L3 | Laboratorio Centro | Lazio | Roma | 70 | 8 | 5 | 82% | 90% | 48 | No | Low
L4 | Laboratorio Est | Emilia-Romagna | Modena | 95 | 8 | 5 | 78% | 89% | 48 | No | Medium
L5 | Atelier Toscana | Tuscany | Prato | 42 | 8 | 5 | 79% | 88% | 45 | No | Low
L6 | Unità Sud | Puglia | Bari | 110 | 8 | 5 | 76% | 87% | 48 | Yes | Medium
L7 | Iberia Garments | Porto | Porto | 180 | 8 | 5 | 80% | 91% | 48 | Yes | Medium
L8 | Balkan Stitch | Transylvania | Cluj | 140 | 8 | 5 | 77% | 88% | 48 | Yes | Medium
L9 | Marmara Apparel | Istanbul | Istanbul | 260 | 8 | 6 | 82% | 90% | 54 | Yes | High
L10 | Tunis Craft Unit | Tunis | Tunis | 210 | 8 | 5 | 79% | 89% | 48 | Yes | Medium

## line_capacity
lab_id | line_id | line_type | primary_product | operators | machines | shift_hours | days_per_week | efficiency | uptime | overtime_allowed | weekly_capacity_hours | net_minutes_day | available_smv_minutes_day
L1 | LN-001 | cutting | Pantalone | 2 | 1 | 8 | 5 | 84% | 92% | No | 40 | 960 | 741.888
L1 | LN-002 | sewing | Body | 5 | 5 | 8 | 5 | 84% | 92% | No | 40 | 2400 | 1854.72
L1 | LN-003 | finishing | Body | 2 | 2 | 8 | 5 | 84% | 92% | No | 40 | 960 | 741.888
L1 | LN-004 | quality_control | T-shirt | 4 | 0 | 8 | 5 | 84% | 92% | No | 40 | 1920 | 1483.776
L1 | LN-005 | sampling | Top | 5 | 3 | 8 | 5 | 84% | 92% | No | 40 | 2400 | 1854.72
L2 | LN-006 | cutting | Top | 2 | 1 | 8 | 5 | 81% | 90% | Yes | 40 | 960 | 699.84
L2 | LN-007 | sewing | Felpa | 6 | 6 | 8 | 5 | 81% | 90% | Yes | 40 | 2880 | 2099.52
L2 | LN-008 | finishing | Jeans | 2 | 2 | 8 | 5 | 81% | 90% | Yes | 40 | 960 | 699.84
L2 | LN-009 | quality_control | Top | 4 | 0 | 8 | 5 | 81% | 90% | Yes | 40 | 1920 | 1399.68
L3 | LN-010 | cutting | Kimono | 3 | 1 | 8 | 5 | 82% | 90% | No | 40 | 1440 | 1062.72
L3 | LN-011 | sewing | Felpa | 5 | 3 | 8 | 5 | 82% | 90% | No | 40 | 2400 | 1771.2
L3 | LN-012 | finishing | Gonna | 5 | 4 | 8 | 5 | 82% | 90% | No | 40 | 2400 | 1771.2
L3 | LN-013 | quality_control | Bra | 2 | 0 | 8 | 5 | 82% | 90% | No | 40 | 960 | 708.48
L3 | LN-014 | sampling | Cappotto | 4 | 4 | 8 | 5 | 82% | 90% | No | 40 | 1920 | 1416.96
L4 | LN-015 | cutting | Felpa | 4 | 4 | 8 | 5 | 78% | 89% | No | 40 | 1920 | 1332.864
L4 | LN-016 | sewing | Boxer | 7 | 5 | 8 | 5 | 78% | 89% | No | 40 | 3360 | 2332.512
L4 | LN-017 | finishing | Cappotto | 5 | 3 | 8 | 5 | 78% | 89% | No | 40 | 2400 | 1666.08
L4 | LN-018 | quality_control | Camicia | 2 | 0 | 8 | 5 | 78% | 89% | No | 40 | 960 | 666.432
L4 | LN-019 | washing | Gonna | 3 | 1 | 8 | 5 | 78% | 89% | No | 40 | 1440 | 999.648
L5 | LN-020 | cutting | Jeans | 4 | 2 | 8 | 5 | 79% | 88% | No | 40 | 1920 | 1334.784
L5 | LN-021 | sewing | Gonna | 6 | 6 | 8 | 5 | 79% | 88% | No | 40 | 2880 | 2002.176
L5 | LN-022 | finishing | Gonna | 4 | 3 | 8 | 5 | 79% | 88% | No | 40 | 1920 | 1334.784
L5 | LN-023 | quality_control | Pantalone | 4 | 0 | 8 | 5 | 79% | 88% | No | 40 | 1920 | 1334.784
L5 | LN-024 | sampling | Abito | 3 | 1 | 8 | 5 | 79% | 88% | No | 40 | 1440 | 1001.088
L6 | LN-025 | cutting | Bra | 5 | 3 | 8 | 5 | 76% | 87% | No | 40 | 2400 | 1586.88
L6 | LN-026 | sewing | T-shirt | 8 | 8 | 8 | 5 | 76% | 87% | No | 40 | 3840 | 2539.008
L6 | LN-027 | finishing | Cappotto | 4 | 3 | 8 | 5 | 76% | 87% | No | 40 | 1920 | 1269.504
L6 | LN-028 | quality_control | Kimono | 3 | 0 | 8 | 5 | 76% | 87% | No | 40 | 1440 | 952.128
L7 | LN-029 | cutting | Blazer | 8 | 6 | 8 | 5 | 80% | 91% | No | 40 | 3840 | 2795.52
L7 | LN-030 | sewing | Abito | 15 | 15 | 8 | 5 | 80% | 91% | No | 40 | 7200 | 5241.6
L7 | LN-031 | finishing | Baby doll | 8 | 8 | 8 | 5 | 80% | 91% | No | 40 | 3840 | 2795.52
L7 | LN-032 | quality_control | Pantalone | 4 | 0 | 8 | 5 | 80% | 91% | No | 40 | 1920 | 1397.76
L7 | LN-033 | washing | Top | 6 | 5 | 8 | 5 | 80% | 91% | No | 40 | 2880 | 2096.64
L8 | LN-034 | cutting | Cappotto | 5 | 5 | 8 | 5 | 77% | 88% | No | 40 | 2400 | 1626.24
L8 | LN-035 | sewing | Kimono | 11 | 10 | 8 | 5 | 77% | 88% | No | 40 | 5280 | 3577.728
L8 | LN-036 | finishing | Felpa | 6 | 6 | 8 | 5 | 77% | 88% | No | 40 | 2880 | 1951.488
L8 | LN-037 | quality_control | Slip | 5 | 0 | 8 | 5 | 77% | 88% | No | 40 | 2400 | 1626.24
L9 | LN-038 | cutting | Abito | 10 | 10 | 8 | 6 | 82% | 90% | No | 48 | 4800 | 3542.4
L9 | LN-039 | sewing | Felpa | 21 | 21 | 8 | 6 | 82% | 90% | No | 48 | 10080 | 7439.04
L9 | LN-040 | finishing | Bra | 8 | 8 | 8 | 6 | 82% | 90% | No | 48 | 3840 | 2833.92
L9 | LN-041 | quality_control | Kimono | 7 | 0 | 8 | 6 | 82% | 90% | No | 48 | 3360 | 2479.68
L9 | LN-042 | washing | Abito | 8 | 6 | 8 | 6 | 82% | 90% | No | 48 | 3840 | 2833.92
L10 | LN-043 | cutting | Pantalone | 9 | 7 | 8 | 5 | 79% | 89% | No | 40 | 4320 | 3037.392
L10 | LN-044 | sewing | Bra | 17 | 17 | 8 | 5 | 79% | 89% | No | 40 | 8160 | 5737.296
L10 | LN-045 | finishing | Pantalone | 6 | 4 | 8 | 5 | 79% | 89% | No | 40 | 2880 | 2024.928
L10 | LN-046 | quality_control | Bra | 6 | 0 | 8 | 5 | 79% | 89% | No | 40 | 2880 | 2024.928

## phase_capacity
lab_id | phase_name | line_type | workers_total | workers_assigned | machines_total | available_minutes_per_day | efficiency | uptime | bottleneck_flag
L1 | adesivazione | cutting | 2 | 2 | 2 | 741.888 | 84% | 92% | OK
L1 | applicazione elastici | sewing | 4 | 3 | 2 | 1112.832 | 84% | 92% | OK
L1 | applicazione fodera | sewing | 3 | 3 | 2 | 1112.832 | 84% | 92% | OK
L1 | applicazione zip | sewing | 6 | 4 | 3 | 1483.776 | 84% | 92% | OK
L1 | asolatura/bottoni | sewing | 3 | 3 | 2 | 1112.832 | 84% | 92% | OK
L1 | assemblaggio | sewing | 6 | 5 | 4 | 1854.72 | 84% | 92% | OK
L1 | assemblaggio busto | sewing | 4 | 3 | 3 | 1112.832 | 84% | 92% | OK
L1 | bottoni automatici | sewing | 2 | 1 | 1 | 370.944 | 84% | 92% | Potential bottleneck
L1 | cappuccio/collo | sewing | 3 | 3 | 2 | 1112.832 | 84% | 92% | OK
L1 | cintura | sewing | 2 | 2 | 1 | 741.888 | 84% | 92% | OK
L1 | collo | sewing | 5 | 3 | 2 | 1112.832 | 84% | 92% | OK
L1 | collo e polsi | sewing | 4 | 2 | 2 | 741.888 | 84% | 92% | OK
L1 | confezione capo | sewing | 8 | 8 | 7 | 2967.552 | 84% | 92% | OK
L1 | confezione corpino | sewing | 3 | 2 | 1 | 741.888 | 84% | 92% | OK
L1 | confezione gonna | sewing | 8 | 7 | 6 | 2596.608 | 84% | 92% | OK
L1 | controllo qualità | quality_control | 1 | 1 | 0 | 370.944 | 84% | 92% | Potential bottleneck
L1 | coppe | sewing | 2 | 1 | 1 | 370.944 | 84% | 92% | Potential bottleneck
L1 | costruzione davanti | sewing | 4 | 2 | 1 | 741.888 | 84% | 92% | OK
L1 | cuciture spalle | sewing | 2 | 1 | 1 | 370.944 | 84% | 92% | Potential bottleneck
L1 | cuciture tasche | sewing | 8 | 6 | 5 | 2225.664 | 84% | 92% | OK
L1 | elastici | sewing | 8 | 6 | 6 | 2225.664 | 84% | 92% | OK
L1 | elastici e spalline | sewing | 3 | 3 | 2 | 1112.832 | 84% | 92% | OK
L1 | elastici/finizioni | sewing | 4 | 3 | 2 | 1112.832 | 84% | 92% | OK
L1 | elastico vita | sewing | 8 | 8 | 8 | 2967.552 | 84% | 92% | OK
L1 | ganci e rifiniture | sewing | 6 | 4 | 3 | 1483.776 | 84% | 92% | OK
L1 | imbastitura | sewing | 6 | 6 | 6 | 2225.664 | 84% | 92% | OK
L1 | maniche | sewing | 2 | 2 | 1 | 741.888 | 84% | 92% | OK
L1 | orlo | sewing | 8 | 7 | 6 | 2596.608 | 84% | 92% | OK
L1 | orlo e rifiniture | sewing | 3 | 1 | 1 | 370.944 | 84% | 92% | Potential bottleneck
L1 | packing | finishing | 3 | 1 | 1 | 370.944 | 84% | 92% | Potential bottleneck
L1 | polsi e fondo | sewing | 3 | 2 | 1 | 741.888 | 84% | 92% | OK
L1 | spalle e fianchi | sewing | 6 | 5 | 4 | 1854.72 | 84% | 92% | OK
L1 | stiro finale | finishing | 3 | 2 | 2 | 741.888 | 84% | 92% | OK
L1 | stiro intermedio | finishing | 3 | 2 | 2 | 741.888 | 84% | 92% | OK
L1 | stiro/packing | finishing | 4 | 2 | 1 | 741.888 | 84% | 92% | OK
L1 | taglio tessuto | cutting | 1 | 1 | 1 | 370.944 | 84% | 92% | Potential bottleneck
L1 | tasche | sewing | 4 | 2 | 2 | 741.888 | 84% | 92% | OK
L2 | adesivazione | cutting | 1 | 1 | 1 | 349.92 | 81% | 90% | Potential bottleneck
L2 | applicazione elastici | sewing | 3 | 1 | 1 | 349.92 | 81% | 90% | Potential bottleneck
L2 | applicazione fodera | sewing | 3 | 1 | 1 | 349.92 | 81% | 90% | Potential bottleneck
L2 | applicazione zip | sewing | 2 | 1 | 1 | 349.92 | 81% | 90% | Potential bottleneck
L2 | asolatura/bottoni | sewing | 3 | 3 | 2 | 1049.76 | 81% | 90% | OK
L2 | assemblaggio | sewing | 4 | 3 | 3 | 1049.76 | 81% | 90% | OK
L2 | assemblaggio busto | sewing | 5 | 3 | 3 | 1049.76 | 81% | 90% | OK
L2 | bottoni automatici | sewing | 5 | 3 | 2 | 1049.76 | 81% | 90% | OK
L2 | cappuccio/collo | sewing | 8 | 6 | 6 | 2099.52 | 81% | 90% | OK
L2 | cintura | sewing | 7 | 7 | 7 | 2449.44 | 81% | 90% | OK
L2 | collo | sewing | 6 | 5 | 4 | 1749.6 | 81% | 90% | OK
L2 | collo e polsi | sewing | 6 | 5 | 4 | 1749.6 | 81% | 90% | OK
L2 | confezione capo | sewing | 3 | 2 | 1 | 699.84 | 81% | 90% | Potential bottleneck
L2 | confezione corpino | sewing | 6 | 5 | 4 | 1749.6 | 81% | 90% | OK
L2 | confezione gonna | sewing | 6 | 5 | 5 | 1749.6 | 81% | 90% | OK
L2 | controllo qualità | quality_control | 2 | 1 | 0 | 349.92 | 81% | 90% | Potential bottleneck
L2 | coppe | sewing | 6 | 5 | 5 | 1749.6 | 81% | 90% | OK
L2 | costruzione davanti | sewing | 4 | 3 | 3 | 1049.76 | 81% | 90% | OK
L2 | cuciture spalle | sewing | 7 | 5 | 4 | 1749.6 | 81% | 90% | OK
L2 | cuciture tasche | sewing | 4 | 3 | 2 | 1049.76 | 81% | 90% | OK
L2 | elastici | sewing | 6 | 4 | 3 | 1399.68 | 81% | 90% | OK
L2 | elastici e spalline | sewing | 4 | 4 | 3 | 1399.68 | 81% | 90% | OK
L2 | elastici/finizioni | sewing | 5 | 4 | 4 | 1399.68 | 81% | 90% | OK
L2 | elastico vita | sewing | 4 | 4 | 3 | 1399.68 | 81% | 90% | OK
L2 | ganci e rifiniture | sewing | 7 | 7 | 6 | 2449.44 | 81% | 90% | OK
L2 | imbastitura | sewing | 5 | 3 | 2 | 1049.76 | 81% | 90% | OK
L2 | maniche | sewing | 7 | 6 | 6 | 2099.52 | 81% | 90% | OK
L2 | orlo | sewing | 3 | 1 | 1 | 349.92 | 81% | 90% | Potential bottleneck
L2 | orlo e rifiniture | sewing | 6 | 4 | 3 | 1399.68 | 81% | 90% | OK
L2 | packing | finishing | 2 | 2 | 2 | 699.84 | 81% | 90% | Potential bottleneck
L2 | polsi e fondo | sewing | 3 | 3 | 3 | 1049.76 | 81% | 90% | OK
L2 | spalle e fianchi | sewing | 7 | 7 | 7 | 2449.44 | 81% | 90% | OK
L2 | stiro finale | finishing | 1 | 1 | 1 | 349.92 | 81% | 90% | Potential bottleneck
L2 | stiro intermedio | finishing | 4 | 4 | 4 | 1399.68 | 81% | 90% | OK
L2 | stiro/packing | finishing | 1 | 1 | 1 | 349.92 | 81% | 90% | Potential bottleneck
L2 | taglio tessuto | cutting | 4 | 2 | 1 | 699.84 | 81% | 90% | Potential bottleneck
L2 | tasche | sewing | 5 | 3 | 3 | 1049.76 | 81% | 90% | OK
L3 | adesivazione | cutting | 3 | 2 | 1 | 708.48 | 82% | 90% | Potential bottleneck
L3 | applicazione elastici | sewing | 7 | 7 | 7 | 2479.68 | 82% | 90% | OK
L3 | applicazione fodera | sewing | 7 | 5 | 5 | 1771.2 | 82% | 90% | OK
L3 | applicazione zip | sewing | 6 | 4 | 4 | 1416.96 | 82% | 90% | OK
L3 | asolatura/bottoni | sewing | 3 | 2 | 2 | 708.48 | 82% | 90% | Potential bottleneck
L3 | assemblaggio | sewing | 2 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L3 | assemblaggio busto | sewing | 3 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L3 | bottoni automatici | sewing | 2 | 2 | 1 | 708.48 | 82% | 90% | Potential bottleneck
L3 | cappuccio/collo | sewing | 6 | 4 | 4 | 1416.96 | 82% | 90% | OK
L3 | cintura | sewing | 4 | 3 | 2 | 1062.72 | 82% | 90% | OK
L3 | collo | sewing | 7 | 5 | 4 | 1771.2 | 82% | 90% | OK
L3 | collo e polsi | sewing | 3 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L3 | confezione capo | sewing | 4 | 4 | 4 | 1416.96 | 82% | 90% | OK
L3 | confezione corpino | sewing | 4 | 4 | 3 | 1416.96 | 82% | 90% | OK
L3 | confezione gonna | sewing | 7 | 6 | 6 | 2125.44 | 82% | 90% | OK
L3 | controllo qualità | quality_control | 1 | 1 | 0 | 354.24 | 82% | 90% | Potential bottleneck
L3 | coppe | sewing | 4 | 3 | 3 | 1062.72 | 82% | 90% | OK
L3 | costruzione davanti | sewing | 3 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L3 | cuciture spalle | sewing | 8 | 7 | 6 | 2479.68 | 82% | 90% | OK
L3 | cuciture tasche | sewing | 2 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L3 | elastici | sewing | 3 | 3 | 2 | 1062.72 | 82% | 90% | OK
L3 | elastici e spalline | sewing | 4 | 4 | 4 | 1416.96 | 82% | 90% | OK
L3 | elastici/finizioni | sewing | 4 | 3 | 3 | 1062.72 | 82% | 90% | OK
L3 | elastico vita | sewing | 5 | 4 | 3 | 1416.96 | 82% | 90% | OK
L3 | ganci e rifiniture | sewing | 4 | 2 | 2 | 708.48 | 82% | 90% | Potential bottleneck
L3 | imbastitura | sewing | 4 | 2 | 1 | 708.48 | 82% | 90% | Potential bottleneck
L3 | maniche | sewing | 7 | 7 | 7 | 2479.68 | 82% | 90% | OK
L3 | orlo | sewing | 7 | 7 | 6 | 2479.68 | 82% | 90% | OK
L3 | orlo e rifiniture | sewing | 4 | 4 | 3 | 1416.96 | 82% | 90% | OK
L3 | packing | finishing | 3 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L3 | polsi e fondo | sewing | 7 | 6 | 5 | 2125.44 | 82% | 90% | OK
L3 | spalle e fianchi | sewing | 6 | 6 | 6 | 2125.44 | 82% | 90% | OK
L3 | stiro finale | finishing | 2 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L3 | stiro intermedio | finishing | 4 | 2 | 1 | 708.48 | 82% | 90% | Potential bottleneck
L3 | stiro/packing | finishing | 4 | 2 | 1 | 708.48 | 82% | 90% | Potential bottleneck
L3 | taglio tessuto | cutting | 2 | 2 | 2 | 708.48 | 82% | 90% | Potential bottleneck
L3 | tasche | sewing | 6 | 5 | 4 | 1771.2 | 82% | 90% | OK
L4 | adesivazione | cutting | 1 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | applicazione elastici | sewing | 2 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | applicazione fodera | sewing | 6 | 4 | 4 | 1332.864 | 78% | 89% | OK
L4 | applicazione zip | sewing | 3 | 2 | 1 | 666.432 | 78% | 89% | Potential bottleneck
L4 | asolatura/bottoni | sewing | 2 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | assemblaggio | sewing | 7 | 5 | 4 | 1666.08 | 78% | 89% | OK
L4 | assemblaggio busto | sewing | 2 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | bottoni automatici | sewing | 8 | 8 | 7 | 2665.728 | 78% | 89% | OK
L4 | cappuccio/collo | sewing | 3 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | cintura | sewing | 5 | 3 | 3 | 999.648 | 78% | 89% | OK
L4 | collo | sewing | 6 | 5 | 4 | 1666.08 | 78% | 89% | OK
L4 | collo e polsi | sewing | 7 | 7 | 6 | 2332.512 | 78% | 89% | OK
L4 | confezione capo | sewing | 4 | 4 | 4 | 1332.864 | 78% | 89% | OK
L4 | confezione corpino | sewing | 6 | 6 | 6 | 1999.296 | 78% | 89% | OK
L4 | confezione gonna | sewing | 5 | 4 | 4 | 1332.864 | 78% | 89% | OK
L4 | controllo qualità | quality_control | 1 | 1 | 0 | 333.216 | 78% | 89% | Potential bottleneck
L4 | coppe | sewing | 5 | 5 | 4 | 1666.08 | 78% | 89% | OK
L4 | costruzione davanti | sewing | 5 | 5 | 5 | 1666.08 | 78% | 89% | OK
L4 | cuciture spalle | sewing | 8 | 6 | 5 | 1999.296 | 78% | 89% | OK
L4 | cuciture tasche | sewing | 4 | 3 | 2 | 999.648 | 78% | 89% | OK
L4 | elastici | sewing | 8 | 7 | 6 | 2332.512 | 78% | 89% | OK
L4 | elastici e spalline | sewing | 2 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | elastici/finizioni | sewing | 7 | 6 | 6 | 1999.296 | 78% | 89% | OK
L4 | elastico vita | sewing | 3 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | ganci e rifiniture | sewing | 6 | 6 | 6 | 1999.296 | 78% | 89% | OK
L4 | imbastitura | sewing | 8 | 8 | 8 | 2665.728 | 78% | 89% | OK
L4 | lavaggio/trattamenti | washing | 3 | 2 | 1 | 666.432 | 78% | 89% | Potential bottleneck
L4 | maniche | sewing | 6 | 5 | 5 | 1666.08 | 78% | 89% | OK
L4 | orlo | sewing | 3 | 2 | 1 | 666.432 | 78% | 89% | Potential bottleneck
L4 | orlo e rifiniture | sewing | 3 | 2 | 2 | 666.432 | 78% | 89% | Potential bottleneck
L4 | packing | finishing | 1 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | polsi e fondo | sewing | 6 | 6 | 6 | 1999.296 | 78% | 89% | OK
L4 | spalle e fianchi | sewing | 3 | 3 | 3 | 999.648 | 78% | 89% | OK
L4 | stiro finale | finishing | 1 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | stiro intermedio | finishing | 2 | 1 | 1 | 333.216 | 78% | 89% | Potential bottleneck
L4 | stiro/packing | finishing | 4 | 3 | 3 | 999.648 | 78% | 89% | OK
L4 | taglio tessuto | cutting | 2 | 2 | 2 | 666.432 | 78% | 89% | Potential bottleneck
L4 | tasche | sewing | 6 | 5 | 5 | 1666.08 | 78% | 89% | OK
L5 | adesivazione | cutting | 3 | 1 | 1 | 333.696 | 79% | 88% | Potential bottleneck
L5 | applicazione elastici | sewing | 3 | 2 | 2 | 667.392 | 79% | 88% | Potential bottleneck
L5 | applicazione fodera | sewing | 7 | 5 | 5 | 1668.48 | 79% | 88% | OK
L5 | applicazione zip | sewing | 5 | 4 | 3 | 1334.784 | 79% | 88% | OK
L5 | asolatura/bottoni | sewing | 2 | 1 | 1 | 333.696 | 79% | 88% | Potential bottleneck
L5 | assemblaggio | sewing | 7 | 5 | 4 | 1668.48 | 79% | 88% | OK
L5 | assemblaggio busto | sewing | 6 | 5 | 5 | 1668.48 | 79% | 88% | OK
L5 | bottoni automatici | sewing | 4 | 2 | 1 | 667.392 | 79% | 88% | Potential bottleneck
L5 | cappuccio/collo | sewing | 8 | 6 | 5 | 2002.176 | 79% | 88% | OK
L5 | cintura | sewing | 7 | 6 | 5 | 2002.176 | 79% | 88% | OK
L5 | collo | sewing | 3 | 2 | 1 | 667.392 | 79% | 88% | Potential bottleneck
L5 | collo e polsi | sewing | 3 | 1 | 1 | 333.696 | 79% | 88% | Potential bottleneck
L5 | confezione capo | sewing | 3 | 3 | 2 | 1001.088 | 79% | 88% | OK
L5 | confezione corpino | sewing | 8 | 6 | 6 | 2002.176 | 79% | 88% | OK
L5 | confezione gonna | sewing | 8 | 7 | 7 | 2335.872 | 79% | 88% | OK
L5 | controllo qualità | quality_control | 4 | 3 | 0 | 1001.088 | 79% | 88% | OK
L5 | coppe | sewing | 6 | 4 | 4 | 1334.784 | 79% | 88% | OK
L5 | costruzione davanti | sewing | 5 | 5 | 4 | 1668.48 | 79% | 88% | OK
L5 | cuciture spalle | sewing | 3 | 2 | 2 | 667.392 | 79% | 88% | Potential bottleneck
L5 | cuciture tasche | sewing | 5 | 4 | 4 | 1334.784 | 79% | 88% | OK
L5 | elastici | sewing | 6 | 4 | 4 | 1334.784 | 79% | 88% | OK
L5 | elastici e spalline | sewing | 2 | 1 | 1 | 333.696 | 79% | 88% | Potential bottleneck
L5 | elastici/finizioni | sewing | 7 | 5 | 5 | 1668.48 | 79% | 88% | OK
L5 | elastico vita | sewing | 8 | 8 | 8 | 2669.568 | 79% | 88% | OK
L5 | ganci e rifiniture | sewing | 8 | 6 | 6 | 2002.176 | 79% | 88% | OK
L5 | imbastitura | sewing | 5 | 5 | 4 | 1668.48 | 79% | 88% | OK
L5 | maniche | sewing | 4 | 4 | 4 | 1334.784 | 79% | 88% | OK
L5 | orlo | sewing | 3 | 1 | 1 | 333.696 | 79% | 88% | Potential bottleneck
L5 | orlo e rifiniture | sewing | 7 | 6 | 6 | 2002.176 | 79% | 88% | OK
L5 | packing | finishing | 2 | 1 | 1 | 333.696 | 79% | 88% | Potential bottleneck
L5 | polsi e fondo | sewing | 6 | 5 | 4 | 1668.48 | 79% | 88% | OK
L5 | spalle e fianchi | sewing | 5 | 4 | 3 | 1334.784 | 79% | 88% | OK
L5 | stiro finale | finishing | 3 | 2 | 1 | 667.392 | 79% | 88% | Potential bottleneck
L5 | stiro intermedio | finishing | 4 | 3 | 3 | 1001.088 | 79% | 88% | OK
L5 | stiro/packing | finishing | 4 | 3 | 3 | 1001.088 | 79% | 88% | OK
L5 | taglio tessuto | cutting | 3 | 2 | 1 | 667.392 | 79% | 88% | Potential bottleneck
L5 | tasche | sewing | 2 | 1 | 1 | 333.696 | 79% | 88% | Potential bottleneck
L6 | adesivazione | cutting | 2 | 2 | 1 | 634.752 | 76% | 87% | Potential bottleneck
L6 | applicazione elastici | sewing | 6 | 4 | 3 | 1269.504 | 76% | 87% | OK
L6 | applicazione fodera | sewing | 4 | 4 | 4 | 1269.504 | 76% | 87% | OK
L6 | applicazione zip | sewing | 4 | 4 | 3 | 1269.504 | 76% | 87% | OK
L6 | asolatura/bottoni | sewing | 6 | 6 | 5 | 1904.256 | 76% | 87% | OK
L6 | assemblaggio | sewing | 6 | 4 | 3 | 1269.504 | 76% | 87% | OK
L6 | assemblaggio busto | sewing | 4 | 3 | 2 | 952.128 | 76% | 87% | OK
L6 | bottoni automatici | sewing | 5 | 5 | 4 | 1586.88 | 76% | 87% | OK
L6 | cappuccio/collo | sewing | 3 | 3 | 2 | 952.128 | 76% | 87% | OK
L6 | cintura | sewing | 3 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | collo | sewing | 6 | 6 | 6 | 1904.256 | 76% | 87% | OK
L6 | collo e polsi | sewing | 8 | 6 | 6 | 1904.256 | 76% | 87% | OK
L6 | confezione capo | sewing | 8 | 8 | 7 | 2539.008 | 76% | 87% | OK
L6 | confezione corpino | sewing | 3 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | confezione gonna | sewing | 2 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | controllo qualità | quality_control | 1 | 1 | 0 | 317.376 | 76% | 87% | Potential bottleneck
L6 | coppe | sewing | 6 | 5 | 4 | 1586.88 | 76% | 87% | OK
L6 | costruzione davanti | sewing | 2 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | cuciture spalle | sewing | 7 | 6 | 6 | 1904.256 | 76% | 87% | OK
L6 | cuciture tasche | sewing | 2 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | elastici | sewing | 2 | 2 | 1 | 634.752 | 76% | 87% | Potential bottleneck
L6 | elastici e spalline | sewing | 6 | 5 | 5 | 1586.88 | 76% | 87% | OK
L6 | elastici/finizioni | sewing | 6 | 4 | 3 | 1269.504 | 76% | 87% | OK
L6 | elastico vita | sewing | 8 | 8 | 8 | 2539.008 | 76% | 87% | OK
L6 | ganci e rifiniture | sewing | 2 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | imbastitura | sewing | 3 | 3 | 2 | 952.128 | 76% | 87% | OK
L6 | maniche | sewing | 8 | 7 | 6 | 2221.632 | 76% | 87% | OK
L6 | orlo | sewing | 8 | 7 | 7 | 2221.632 | 76% | 87% | OK
L6 | orlo e rifiniture | sewing | 4 | 3 | 2 | 952.128 | 76% | 87% | OK
L6 | packing | finishing | 2 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | polsi e fondo | sewing | 4 | 2 | 2 | 634.752 | 76% | 87% | Potential bottleneck
L6 | spalle e fianchi | sewing | 7 | 5 | 5 | 1586.88 | 76% | 87% | OK
L6 | stiro finale | finishing | 1 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | stiro intermedio | finishing | 4 | 2 | 1 | 634.752 | 76% | 87% | Potential bottleneck
L6 | stiro/packing | finishing | 1 | 1 | 1 | 317.376 | 76% | 87% | Potential bottleneck
L6 | taglio tessuto | cutting | 2 | 2 | 1 | 634.752 | 76% | 87% | Potential bottleneck
L6 | tasche | sewing | 8 | 7 | 6 | 2221.632 | 76% | 87% | OK
L7 | adesivazione | cutting | 1 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | applicazione elastici | sewing | 3 | 3 | 2 | 1048.32 | 80% | 91% | OK
L7 | applicazione fodera | sewing | 4 | 4 | 4 | 1397.76 | 80% | 91% | OK
L7 | applicazione zip | sewing | 7 | 6 | 6 | 2096.64 | 80% | 91% | OK
L7 | asolatura/bottoni | sewing | 3 | 2 | 2 | 698.88 | 80% | 91% | Potential bottleneck
L7 | assemblaggio | sewing | 3 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | assemblaggio busto | sewing | 8 | 6 | 5 | 2096.64 | 80% | 91% | OK
L7 | bottoni automatici | sewing | 2 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | cappuccio/collo | sewing | 6 | 6 | 5 | 2096.64 | 80% | 91% | OK
L7 | cintura | sewing | 7 | 5 | 4 | 1747.2 | 80% | 91% | OK
L7 | collo | sewing | 5 | 3 | 3 | 1048.32 | 80% | 91% | OK
L7 | collo e polsi | sewing | 8 | 6 | 6 | 2096.64 | 80% | 91% | OK
L7 | confezione capo | sewing | 6 | 4 | 3 | 1397.76 | 80% | 91% | OK
L7 | confezione corpino | sewing | 2 | 2 | 1 | 698.88 | 80% | 91% | Potential bottleneck
L7 | confezione gonna | sewing | 3 | 3 | 2 | 1048.32 | 80% | 91% | OK
L7 | controllo qualità | quality_control | 4 | 3 | 0 | 1048.32 | 80% | 91% | OK
L7 | coppe | sewing | 2 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | costruzione davanti | sewing | 8 | 7 | 6 | 2446.08 | 80% | 91% | OK
L7 | cuciture spalle | sewing | 3 | 2 | 1 | 698.88 | 80% | 91% | Potential bottleneck
L7 | cuciture tasche | sewing | 5 | 5 | 4 | 1747.2 | 80% | 91% | OK
L7 | elastici | sewing | 2 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | elastici e spalline | sewing | 8 | 8 | 8 | 2795.52 | 80% | 91% | OK
L7 | elastici/finizioni | sewing | 2 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | elastico vita | sewing | 5 | 3 | 3 | 1048.32 | 80% | 91% | OK
L7 | ganci e rifiniture | sewing | 7 | 6 | 5 | 2096.64 | 80% | 91% | OK
L7 | imbastitura | sewing | 4 | 4 | 4 | 1397.76 | 80% | 91% | OK
L7 | lavaggio/trattamenti | washing | 1 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | maniche | sewing | 4 | 3 | 3 | 1048.32 | 80% | 91% | OK
L7 | orlo | sewing | 3 | 3 | 3 | 1048.32 | 80% | 91% | OK
L7 | orlo e rifiniture | sewing | 5 | 4 | 3 | 1397.76 | 80% | 91% | OK
L7 | packing | finishing | 1 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | polsi e fondo | sewing | 4 | 2 | 2 | 698.88 | 80% | 91% | Potential bottleneck
L7 | spalle e fianchi | sewing | 6 | 4 | 3 | 1397.76 | 80% | 91% | OK
L7 | stiro finale | finishing | 4 | 4 | 3 | 1397.76 | 80% | 91% | OK
L7 | stiro intermedio | finishing | 4 | 3 | 3 | 1048.32 | 80% | 91% | OK
L7 | stiro/packing | finishing | 2 | 1 | 1 | 349.44 | 80% | 91% | Potential bottleneck
L7 | taglio tessuto | cutting | 4 | 4 | 4 | 1397.76 | 80% | 91% | OK
L7 | tasche | sewing | 4 | 3 | 2 | 1048.32 | 80% | 91% | OK
L8 | adesivazione | cutting | 4 | 4 | 4 | 1300.992 | 77% | 88% | OK
L8 | applicazione elastici | sewing | 3 | 2 | 1 | 650.496 | 77% | 88% | Potential bottleneck
L8 | applicazione fodera | sewing | 5 | 4 | 3 | 1300.992 | 77% | 88% | OK
L8 | applicazione zip | sewing | 8 | 8 | 7 | 2601.984 | 77% | 88% | OK
L8 | asolatura/bottoni | sewing | 4 | 4 | 3 | 1300.992 | 77% | 88% | OK
L8 | assemblaggio | sewing | 6 | 4 | 4 | 1300.992 | 77% | 88% | OK
L8 | assemblaggio busto | sewing | 5 | 5 | 5 | 1626.24 | 77% | 88% | OK
L8 | bottoni automatici | sewing | 4 | 4 | 3 | 1300.992 | 77% | 88% | OK
L8 | cappuccio/collo | sewing | 4 | 2 | 1 | 650.496 | 77% | 88% | Potential bottleneck
L8 | cintura | sewing | 8 | 7 | 6 | 2276.736 | 77% | 88% | OK
L8 | collo | sewing | 4 | 3 | 3 | 975.744 | 77% | 88% | OK
L8 | collo e polsi | sewing | 4 | 3 | 3 | 975.744 | 77% | 88% | OK
L8 | confezione capo | sewing | 5 | 4 | 4 | 1300.992 | 77% | 88% | OK
L8 | confezione corpino | sewing | 5 | 4 | 3 | 1300.992 | 77% | 88% | OK
L8 | confezione gonna | sewing | 7 | 5 | 4 | 1626.24 | 77% | 88% | OK
L8 | controllo qualità | quality_control | 2 | 1 | 0 | 325.248 | 77% | 88% | Potential bottleneck
L8 | coppe | sewing | 5 | 4 | 3 | 1300.992 | 77% | 88% | OK
L8 | costruzione davanti | sewing | 4 | 4 | 4 | 1300.992 | 77% | 88% | OK
L8 | cuciture spalle | sewing | 6 | 4 | 4 | 1300.992 | 77% | 88% | OK
L8 | cuciture tasche | sewing | 7 | 5 | 5 | 1626.24 | 77% | 88% | OK
L8 | elastici | sewing | 7 | 6 | 6 | 1951.488 | 77% | 88% | OK
L8 | elastici e spalline | sewing | 5 | 4 | 4 | 1300.992 | 77% | 88% | OK
L8 | elastici/finizioni | sewing | 8 | 7 | 6 | 2276.736 | 77% | 88% | OK
L8 | elastico vita | sewing | 3 | 1 | 1 | 325.248 | 77% | 88% | Potential bottleneck
L8 | ganci e rifiniture | sewing | 3 | 2 | 2 | 650.496 | 77% | 88% | Potential bottleneck
L8 | imbastitura | sewing | 7 | 6 | 5 | 1951.488 | 77% | 88% | OK
L8 | maniche | sewing | 2 | 1 | 1 | 325.248 | 77% | 88% | Potential bottleneck
L8 | orlo | sewing | 6 | 5 | 4 | 1626.24 | 77% | 88% | OK
L8 | orlo e rifiniture | sewing | 6 | 6 | 5 | 1951.488 | 77% | 88% | OK
L8 | packing | finishing | 1 | 1 | 1 | 325.248 | 77% | 88% | Potential bottleneck
L8 | polsi e fondo | sewing | 7 | 5 | 4 | 1626.24 | 77% | 88% | OK
L8 | spalle e fianchi | sewing | 3 | 1 | 1 | 325.248 | 77% | 88% | Potential bottleneck
L8 | stiro finale | finishing | 4 | 3 | 2 | 975.744 | 77% | 88% | OK
L8 | stiro intermedio | finishing | 1 | 1 | 1 | 325.248 | 77% | 88% | Potential bottleneck
L8 | stiro/packing | finishing | 3 | 3 | 3 | 975.744 | 77% | 88% | OK
L8 | taglio tessuto | cutting | 4 | 3 | 2 | 975.744 | 77% | 88% | OK
L8 | tasche | sewing | 5 | 3 | 3 | 975.744 | 77% | 88% | OK
L9 | adesivazione | cutting | 3 | 3 | 2 | 1062.72 | 82% | 90% | OK
L9 | applicazione elastici | sewing | 2 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L9 | applicazione fodera | sewing | 2 | 2 | 2 | 708.48 | 82% | 90% | Potential bottleneck
L9 | applicazione zip | sewing | 4 | 3 | 2 | 1062.72 | 82% | 90% | OK
L9 | asolatura/bottoni | sewing | 5 | 5 | 4 | 1771.2 | 82% | 90% | OK
L9 | assemblaggio | sewing | 4 | 3 | 3 | 1062.72 | 82% | 90% | OK
L9 | assemblaggio busto | sewing | 5 | 3 | 2 | 1062.72 | 82% | 90% | OK
L9 | bottoni automatici | sewing | 4 | 4 | 3 | 1416.96 | 82% | 90% | OK
L9 | cappuccio/collo | sewing | 2 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L9 | cintura | sewing | 2 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L9 | collo | sewing | 7 | 7 | 7 | 2479.68 | 82% | 90% | OK
L9 | collo e polsi | sewing | 6 | 6 | 6 | 2125.44 | 82% | 90% | OK
L9 | confezione capo | sewing | 4 | 2 | 1 | 708.48 | 82% | 90% | Potential bottleneck
L9 | confezione corpino | sewing | 5 | 5 | 4 | 1771.2 | 82% | 90% | OK
L9 | confezione gonna | sewing | 7 | 7 | 7 | 2479.68 | 82% | 90% | OK
L9 | controllo qualità | quality_control | 4 | 3 | 0 | 1062.72 | 82% | 90% | OK
L9 | coppe | sewing | 2 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L9 | costruzione davanti | sewing | 5 | 3 | 2 | 1062.72 | 82% | 90% | OK
L9 | cuciture spalle | sewing | 5 | 5 | 5 | 1771.2 | 82% | 90% | OK
L9 | cuciture tasche | sewing | 3 | 2 | 2 | 708.48 | 82% | 90% | Potential bottleneck
L9 | elastici | sewing | 6 | 6 | 6 | 2125.44 | 82% | 90% | OK
L9 | elastici e spalline | sewing | 4 | 3 | 3 | 1062.72 | 82% | 90% | OK
L9 | elastici/finizioni | sewing | 5 | 5 | 4 | 1771.2 | 82% | 90% | OK
L9 | elastico vita | sewing | 7 | 6 | 5 | 2125.44 | 82% | 90% | OK
L9 | ganci e rifiniture | sewing | 6 | 5 | 4 | 1771.2 | 82% | 90% | OK
L9 | imbastitura | sewing | 6 | 6 | 5 | 2125.44 | 82% | 90% | OK
L9 | lavaggio/trattamenti | washing | 3 | 2 | 2 | 708.48 | 82% | 90% | Potential bottleneck
L9 | maniche | sewing | 8 | 6 | 5 | 2125.44 | 82% | 90% | OK
L9 | orlo | sewing | 6 | 4 | 4 | 1416.96 | 82% | 90% | OK
L9 | orlo e rifiniture | sewing | 7 | 7 | 6 | 2479.68 | 82% | 90% | OK
L9 | packing | finishing | 1 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L9 | polsi e fondo | sewing | 2 | 2 | 1 | 708.48 | 82% | 90% | Potential bottleneck
L9 | spalle e fianchi | sewing | 7 | 7 | 6 | 2479.68 | 82% | 90% | OK
L9 | stiro finale | finishing | 4 | 2 | 2 | 708.48 | 82% | 90% | Potential bottleneck
L9 | stiro intermedio | finishing | 4 | 3 | 3 | 1062.72 | 82% | 90% | OK
L9 | stiro/packing | finishing | 4 | 2 | 2 | 708.48 | 82% | 90% | Potential bottleneck
L9 | taglio tessuto | cutting | 2 | 1 | 1 | 354.24 | 82% | 90% | Potential bottleneck
L9 | tasche | sewing | 3 | 3 | 2 | 1062.72 | 82% | 90% | OK
L10 | adesivazione | cutting | 4 | 2 | 2 | 674.976 | 79% | 89% | Potential bottleneck
L10 | applicazione elastici | sewing | 8 | 7 | 7 | 2362.416 | 79% | 89% | OK
L10 | applicazione fodera | sewing | 5 | 5 | 5 | 1687.44 | 79% | 89% | OK
L10 | applicazione zip | sewing | 8 | 7 | 6 | 2362.416 | 79% | 89% | OK
L10 | asolatura/bottoni | sewing | 5 | 3 | 2 | 1012.464 | 79% | 89% | OK
L10 | assemblaggio | sewing | 5 | 3 | 2 | 1012.464 | 79% | 89% | OK
L10 | assemblaggio busto | sewing | 5 | 5 | 5 | 1687.44 | 79% | 89% | OK
L10 | bottoni automatici | sewing | 6 | 6 | 6 | 2024.928 | 79% | 89% | OK
L10 | cappuccio/collo | sewing | 4 | 4 | 3 | 1349.952 | 79% | 89% | OK
L10 | cintura | sewing | 3 | 1 | 1 | 337.488 | 79% | 89% | Potential bottleneck
L10 | collo | sewing | 3 | 2 | 1 | 674.976 | 79% | 89% | Potential bottleneck
L10 | collo e polsi | sewing | 6 | 4 | 4 | 1349.952 | 79% | 89% | OK
L10 | confezione capo | sewing | 6 | 6 | 5 | 2024.928 | 79% | 89% | OK
L10 | confezione corpino | sewing | 8 | 6 | 5 | 2024.928 | 79% | 89% | OK
L10 | confezione gonna | sewing | 6 | 6 | 5 | 2024.928 | 79% | 89% | OK
L10 | controllo qualità | quality_control | 2 | 1 | 0 | 337.488 | 79% | 89% | Potential bottleneck
L10 | coppe | sewing | 2 | 1 | 1 | 337.488 | 79% | 89% | Potential bottleneck
L10 | costruzione davanti | sewing | 4 | 4 | 3 | 1349.952 | 79% | 89% | OK
L10 | cuciture spalle | sewing | 4 | 3 | 3 | 1012.464 | 79% | 89% | OK
L10 | cuciture tasche | sewing | 5 | 5 | 5 | 1687.44 | 79% | 89% | OK
L10 | elastici | sewing | 3 | 1 | 1 | 337.488 | 79% | 89% | Potential bottleneck
L10 | elastici e spalline | sewing | 8 | 6 | 5 | 2024.928 | 79% | 89% | OK
L10 | elastici/finizioni | sewing | 3 | 1 | 1 | 337.488 | 79% | 89% | Potential bottleneck
L10 | elastico vita | sewing | 8 | 8 | 8 | 2699.904 | 79% | 89% | OK
L10 | ganci e rifiniture | sewing | 8 | 8 | 7 | 2699.904 | 79% | 89% | OK
L10 | imbastitura | sewing | 6 | 5 | 5 | 1687.44 | 79% | 89% | OK
L10 | maniche | sewing | 4 | 2 | 1 | 674.976 | 79% | 89% | Potential bottleneck
L10 | orlo | sewing | 4 | 2 | 1 | 674.976 | 79% | 89% | Potential bottleneck
L10 | orlo e rifiniture | sewing | 8 | 6 | 6 | 2024.928 | 79% | 89% | OK
L10 | packing | finishing | 2 | 1 | 1 | 337.488 | 79% | 89% | Potential bottleneck
L10 | polsi e fondo | sewing | 4 | 2 | 2 | 674.976 | 79% | 89% | Potential bottleneck
L10 | spalle e fianchi | sewing | 7 | 7 | 7 | 2362.416 | 79% | 89% | OK
L10 | stiro finale | finishing | 2 | 1 | 1 | 337.488 | 79% | 89% | Potential bottleneck
L10 | stiro intermedio | finishing | 2 | 1 | 1 | 337.488 | 79% | 89% | Potential bottleneck
L10 | stiro/packing | finishing | 4 | 4 | 3 | 1349.952 | 79% | 89% | OK
L10 | taglio tessuto | cutting | 4 | 3 | 2 | 1012.464 | 79% | 89% | OK
L10 | tasche | sewing | 2 | 1 | 1 | 337.488 | 79% | 89% | Potential bottleneck

## TNA_calendar
tna_id | order_id | milestone | planned_date | actual_date | delay_days | status | critical_path
TNA-001-01 | ORD-1010 | tech pack freeze | 2026-05-02 | 2026-05-02 | 0 | Done | No
TNA-001-02 | ORD-1010 | BOM final approval | 2026-05-05 |  |  | Open | No
TNA-001-03 | ORD-1010 | fabric booking | 2026-05-07 |  |  | Open | No
TNA-001-04 | ORD-1010 | trim booking | 2026-05-09 | 2026-05-12 | 3 | Delayed | No
TNA-001-05 | ORD-1010 | fit sample sent | 2026-05-13 | 2026-05-11 | -2 | Done | No
TNA-001-06 | ORD-1010 | fit approval | 2026-05-19 |  |  | Open | No
TNA-001-07 | ORD-1010 | size set sample | 2026-05-23 |  |  | Open | No
TNA-001-08 | ORD-1010 | PP sample approval | 2026-05-29 | 2026-06-01 | 3 | Delayed | Yes
TNA-001-09 | ORD-1010 | fabric in-house | 2026-05-31 | 2026-06-01 | 1 | Delayed | Yes
TNA-001-10 | ORD-1010 | bulk cutting start | 2026-06-02 |  |  | Open | Yes
TNA-001-11 | ORD-1010 | sewing start | 2026-06-05 |  |  | Open | Yes
TNA-001-12 | ORD-1010 | inline QC | 2026-06-09 | 2026-06-11 | 2 | Delayed | No
TNA-001-13 | ORD-1010 | finishing & pressing | 2026-06-11 |  |  | Open | No
TNA-001-14 | ORD-1010 | final inspection | 2026-06-13 | 2026-06-14 | 1 | Delayed | Yes
TNA-001-15 | ORD-1010 | packing | 2026-06-14 |  |  | Open | No
TNA-001-16 | ORD-1010 | ex-factory | 2026-06-16 | 2026-06-16 | 0 | Done | Yes
TNA-002-01 | ORD-1011 | tech pack freeze | 2026-04-27 | 2026-04-30 | 3 | Delayed | No
TNA-002-02 | ORD-1011 | BOM final approval | 2026-04-30 |  |  | Open | No
TNA-002-03 | ORD-1011 | fabric booking | 2026-05-02 |  |  | Open | No
TNA-002-04 | ORD-1011 | trim booking | 2026-05-04 |  |  | Open | No
TNA-002-05 | ORD-1011 | fit sample sent | 2026-05-08 | 2026-05-11 | 3 | Delayed | No
TNA-002-06 | ORD-1011 | fit approval | 2026-05-14 | 2026-05-14 | 0 | Done | No
TNA-002-07 | ORD-1011 | size set sample | 2026-05-18 | 2026-05-16 | -2 | Done | No
TNA-002-08 | ORD-1011 | PP sample approval | 2026-05-24 |  |  | Open | Yes
TNA-002-09 | ORD-1011 | fabric in-house | 2026-05-26 | 2026-05-26 | 0 | Done | Yes
TNA-002-10 | ORD-1011 | bulk cutting start | 2026-05-28 |  |  | Open | Yes
TNA-002-11 | ORD-1011 | sewing start | 2026-05-31 | 2026-05-31 | 0 | Done | Yes
TNA-002-12 | ORD-1011 | inline QC | 2026-06-04 | 2026-06-05 | 1 | Delayed | No
TNA-002-13 | ORD-1011 | finishing & pressing | 2026-06-06 | 2026-06-07 | 1 | Delayed | No
TNA-002-14 | ORD-1011 | final inspection | 2026-06-08 |  |  | Open | Yes
TNA-002-15 | ORD-1011 | packing | 2026-06-09 | 2026-06-07 | -2 | Done | No
TNA-002-16 | ORD-1011 | ex-factory | 2026-06-11 | 2026-06-11 | 0 | Done | Yes
TNA-003-01 | ORD-1012 | tech pack freeze | 2026-05-05 |  |  | Open | No
TNA-003-02 | ORD-1012 | BOM final approval | 2026-05-08 |  |  | Open | No
TNA-003-03 | ORD-1012 | fabric booking | 2026-05-10 | 2026-05-09 | -1 | Done | No
TNA-003-04 | ORD-1012 | trim booking | 2026-05-12 |  |  | Open | No
TNA-003-05 | ORD-1012 | fit sample sent | 2026-05-16 | 2026-05-19 | 3 | Delayed | No
TNA-003-06 | ORD-1012 | fit approval | 2026-05-22 | 2026-05-22 | 0 | Done | No
TNA-003-07 | ORD-1012 | size set sample | 2026-05-26 | 2026-05-29 | 3 | Delayed | No
TNA-003-08 | ORD-1012 | PP sample approval | 2026-06-01 | 2026-06-02 | 1 | Delayed | Yes
TNA-003-09 | ORD-1012 | fabric in-house | 2026-06-03 |  |  | Open | Yes
TNA-003-10 | ORD-1012 | bulk cutting start | 2026-06-05 |  |  | Open | Yes
TNA-003-11 | ORD-1012 | sewing start | 2026-06-08 | 2026-06-08 | 0 | Done | Yes
TNA-003-12 | ORD-1012 | inline QC | 2026-06-12 | 2026-06-12 | 0 | Done | No
TNA-003-13 | ORD-1012 | finishing & pressing | 2026-06-14 | 2026-06-13 | -1 | Done | No
TNA-003-14 | ORD-1012 | final inspection | 2026-06-16 | 2026-06-17 | 1 | Delayed | Yes
TNA-003-15 | ORD-1012 | packing | 2026-06-17 |  |  | Open | No
TNA-003-16 | ORD-1012 | ex-factory | 2026-06-19 | 2026-06-19 | 0 | Done | Yes
TNA-004-01 | ORD-1013 | tech pack freeze | 2026-04-25 | 2026-04-25 | 0 | Done | No
TNA-004-02 | ORD-1013 | BOM final approval | 2026-04-28 | 2026-04-26 | -2 | Done | No
TNA-004-03 | ORD-1013 | fabric booking | 2026-04-30 | 2026-04-30 | 0 | Done | No
TNA-004-04 | ORD-1013 | trim booking | 2026-05-02 | 2026-05-02 | 0 | Done | No
TNA-004-05 | ORD-1013 | fit sample sent | 2026-05-06 | 2026-05-06 | 0 | Done | No
TNA-004-06 | ORD-1013 | fit approval | 2026-05-12 |  |  | Open | No
TNA-004-07 | ORD-1013 | size set sample | 2026-05-16 | 2026-05-19 | 3 | Delayed | No
TNA-004-08 | ORD-1013 | PP sample approval | 2026-05-22 |  |  | Open | Yes
TNA-004-09 | ORD-1013 | fabric in-house | 2026-05-24 | 2026-05-23 | -1 | Done | Yes
TNA-004-10 | ORD-1013 | bulk cutting start | 2026-05-26 | 2026-05-25 | -1 | Done | Yes
TNA-004-11 | ORD-1013 | sewing start | 2026-05-29 | 2026-05-31 | 2 | Delayed | Yes
TNA-004-12 | ORD-1013 | inline QC | 2026-06-02 | 2026-06-04 | 2 | Delayed | No
TNA-004-13 | ORD-1013 | finishing & pressing | 2026-06-04 | 2026-06-04 | 0 | Done | No
TNA-004-14 | ORD-1013 | final inspection | 2026-06-06 | 2026-06-05 | -1 | Done | Yes
TNA-004-15 | ORD-1013 | packing | 2026-06-07 | 2026-06-07 | 0 | Done | No
TNA-004-16 | ORD-1013 | ex-factory | 2026-06-09 |  |  | Open | Yes
TNA-005-01 | ORD-1014 | tech pack freeze | 2026-04-30 |  |  | Open | No
TNA-005-02 | ORD-1014 | BOM final approval | 2026-05-03 |  |  | Open | No
TNA-005-03 | ORD-1014 | fabric booking | 2026-05-05 |  |  | Open | No
TNA-005-04 | ORD-1014 | trim booking | 2026-05-07 | 2026-05-12 | 5 | Delayed | No
TNA-005-05 | ORD-1014 | fit sample sent | 2026-05-11 | 2026-05-11 | 0 | Done | No
TNA-005-06 | ORD-1014 | fit approval | 2026-05-17 |  |  | Open | No
TNA-005-07 | ORD-1014 | size set sample | 2026-05-21 | 2026-05-19 | -2 | Done | No
TNA-005-08 | ORD-1014 | PP sample approval | 2026-05-27 |  |  | Open | Yes
TNA-005-09 | ORD-1014 | fabric in-house | 2026-05-29 |  |  | Open | Yes
TNA-005-10 | ORD-1014 | bulk cutting start | 2026-05-31 | 2026-06-02 | 2 | Delayed | Yes
TNA-005-11 | ORD-1014 | sewing start | 2026-06-03 | 2026-06-06 | 3 | Delayed | Yes
TNA-005-12 | ORD-1014 | inline QC | 2026-06-07 | 2026-06-06 | -1 | Done | No
TNA-005-13 | ORD-1014 | finishing & pressing | 2026-06-09 | 2026-06-07 | -2 | Done | No
TNA-005-14 | ORD-1014 | final inspection | 2026-06-11 |  |  | Open | Yes
TNA-005-15 | ORD-1014 | packing | 2026-06-12 |  |  | Open | No
TNA-005-16 | ORD-1014 | ex-factory | 2026-06-14 | 2026-06-16 | 2 | Delayed | Yes
TNA-006-01 | ORD-1106 | tech pack freeze | 2026-06-13 | 2026-06-13 | 0 | Done | No
TNA-006-02 | ORD-1106 | BOM final approval | 2026-06-16 |  |  | Open | No
TNA-006-03 | ORD-1106 | fabric booking | 2026-06-18 |  |  | Open | No
TNA-006-04 | ORD-1106 | trim booking | 2026-06-20 |  |  | Open | No
TNA-006-05 | ORD-1106 | fit sample sent | 2026-06-24 | 2026-06-23 | -1 | Done | No
TNA-006-06 | ORD-1106 | fit approval | 2026-06-30 | 2026-06-30 | 0 | Done | No
TNA-006-07 | ORD-1106 | size set sample | 2026-07-04 | 2026-07-02 | -2 | Done | No
TNA-006-08 | ORD-1106 | PP sample approval | 2026-07-10 |  |  | Open | Yes
TNA-006-09 | ORD-1106 | fabric in-house | 2026-07-12 | 2026-07-12 | 0 | Done | Yes
TNA-006-10 | ORD-1106 | bulk cutting start | 2026-07-14 | 2026-07-19 | 5 | Delayed | Yes
TNA-006-11 | ORD-1106 | sewing start | 2026-07-17 |  |  | Open | Yes
TNA-006-12 | ORD-1106 | inline QC | 2026-07-21 | 2026-07-23 | 2 | Delayed | No
TNA-006-13 | ORD-1106 | finishing & pressing | 2026-07-23 | 2026-07-28 | 5 | Delayed | No
TNA-006-14 | ORD-1106 | final inspection | 2026-07-25 | 2026-07-25 | 0 | Done | Yes
TNA-006-15 | ORD-1106 | packing | 2026-07-26 | 2026-07-26 | 0 | Done | No
TNA-006-16 | ORD-1106 | ex-factory | 2026-07-28 | 2026-07-28 | 0 | Done | Yes
TNA-007-01 | ORD-1107 | tech pack freeze | 2026-07-15 |  |  | Open | No
TNA-007-02 | ORD-1107 | BOM final approval | 2026-07-18 | 2026-07-19 | 1 | Delayed | No
TNA-007-03 | ORD-1107 | fabric booking | 2026-07-20 | 2026-07-19 | -1 | Done | No
TNA-007-04 | ORD-1107 | trim booking | 2026-07-22 | 2026-07-24 | 2 | Delayed | No
TNA-007-05 | ORD-1107 | fit sample sent | 2026-07-26 |  |  | Open | No
TNA-007-06 | ORD-1107 | fit approval | 2026-08-01 |  |  | Open | No
TNA-007-07 | ORD-1107 | size set sample | 2026-08-05 | 2026-08-04 | -1 | Done | No
TNA-007-08 | ORD-1107 | PP sample approval | 2026-08-11 |  |  | Open | Yes
TNA-007-09 | ORD-1107 | fabric in-house | 2026-08-13 | 2026-08-11 | -2 | Done | Yes
TNA-007-10 | ORD-1107 | bulk cutting start | 2026-08-15 | 2026-08-15 | 0 | Done | Yes
TNA-007-11 | ORD-1107 | sewing start | 2026-08-18 | 2026-08-18 | 0 | Done | Yes
TNA-007-12 | ORD-1107 | inline QC | 2026-08-22 |  |  | Open | No
TNA-007-13 | ORD-1107 | finishing & pressing | 2026-08-24 | 2026-08-25 | 1 | Delayed | No
TNA-007-14 | ORD-1107 | final inspection | 2026-08-26 | 2026-08-26 | 0 | Done | Yes
TNA-007-15 | ORD-1107 | packing | 2026-08-27 | 2026-08-27 | 0 | Done | No
TNA-007-16 | ORD-1107 | ex-factory | 2026-08-29 |  |  | Open | Yes
TNA-008-01 | ORD-1108 | tech pack freeze | 2026-07-20 |  |  | Open | No
TNA-008-02 | ORD-1108 | BOM final approval | 2026-07-23 |  |  | Open | No
TNA-008-03 | ORD-1108 | fabric booking | 2026-07-25 | 2026-07-23 | -2 | Done | No
TNA-008-04 | ORD-1108 | trim booking | 2026-07-27 | 2026-07-29 | 2 | Delayed | No
TNA-008-05 | ORD-1108 | fit sample sent | 2026-07-31 | 2026-07-30 | -1 | Done | No
TNA-008-06 | ORD-1108 | fit approval | 2026-08-06 | 2026-08-05 | -1 | Done | No
TNA-008-07 | ORD-1108 | size set sample | 2026-08-10 | 2026-08-15 | 5 | Delayed | No
TNA-008-08 | ORD-1108 | PP sample approval | 2026-08-16 | 2026-08-19 | 3 | Delayed | Yes
TNA-008-09 | ORD-1108 | fabric in-house | 2026-08-18 |  |  | Open | Yes
TNA-008-10 | ORD-1108 | bulk cutting start | 2026-08-20 | 2026-08-20 | 0 | Done | Yes
TNA-008-11 | ORD-1108 | sewing start | 2026-08-23 | 2026-08-22 | -1 | Done | Yes
TNA-008-12 | ORD-1108 | inline QC | 2026-08-27 |  |  | Open | No
TNA-008-13 | ORD-1108 | finishing & pressing | 2026-08-29 |  |  | Open | No
TNA-008-14 | ORD-1108 | final inspection | 2026-08-31 | 2026-09-05 | 5 | Delayed | Yes
TNA-008-15 | ORD-1108 | packing | 2026-09-01 | 2026-08-30 | -2 | Done | No
TNA-008-16 | ORD-1108 | ex-factory | 2026-09-03 | 2026-09-06 | 3 | Delayed | Yes
TNA-009-01 | ORD-1109 | tech pack freeze | 2026-08-01 | 2026-08-01 | 0 | Done | No
TNA-009-02 | ORD-1109 | BOM final approval | 2026-08-04 | 2026-08-02 | -2 | Done | No
TNA-009-03 | ORD-1109 | fabric booking | 2026-08-06 | 2026-08-08 | 2 | Delayed | No
TNA-009-04 | ORD-1109 | trim booking | 2026-08-08 | 2026-08-08 | 0 | Done | No
TNA-009-05 | ORD-1109 | fit sample sent | 2026-08-12 | 2026-08-13 | 1 | Delayed | No
TNA-009-06 | ORD-1109 | fit approval | 2026-08-18 | 2026-08-17 | -1 | Done | No
TNA-009-07 | ORD-1109 | size set sample | 2026-08-22 | 2026-08-21 | -1 | Done | No
TNA-009-08 | ORD-1109 | PP sample approval | 2026-08-28 | 2026-08-26 | -2 | Done | Yes
TNA-009-09 | ORD-1109 | fabric in-house | 2026-08-30 | 2026-09-04 | 5 | Delayed | Yes
TNA-009-10 | ORD-1109 | bulk cutting start | 2026-09-01 |  |  | Open | Yes
TNA-009-11 | ORD-1109 | sewing start | 2026-09-04 |  |  | Open | Yes
TNA-009-12 | ORD-1109 | inline QC | 2026-09-08 | 2026-09-11 | 3 | Delayed | No
TNA-009-13 | ORD-1109 | finishing & pressing | 2026-09-10 |  |  | Open | No
TNA-009-14 | ORD-1109 | final inspection | 2026-09-12 |  |  | Open | Yes
TNA-009-15 | ORD-1109 | packing | 2026-09-13 | 2026-09-12 | -1 | Done | No
TNA-009-16 | ORD-1109 | ex-factory | 2026-09-15 | 2026-09-13 | -2 | Done | Yes
TNA-010-01 | ORD-1110 | tech pack freeze | 2026-04-30 | 2026-04-30 | 0 | Done | No
TNA-010-02 | ORD-1110 | BOM final approval | 2026-05-03 | 2026-05-03 | 0 | Done | No
TNA-010-03 | ORD-1110 | fabric booking | 2026-05-05 |  |  | Open | No
TNA-010-04 | ORD-1110 | trim booking | 2026-05-07 | 2026-05-08 | 1 | Delayed | No
TNA-010-05 | ORD-1110 | fit sample sent | 2026-05-11 | 2026-05-14 | 3 | Delayed | No
TNA-010-06 | ORD-1110 | fit approval | 2026-05-17 |  |  | Open | No
TNA-010-07 | ORD-1110 | size set sample | 2026-05-21 |  |  | Open | No
TNA-010-08 | ORD-1110 | PP sample approval | 2026-05-27 |  |  | Open | Yes
TNA-010-09 | ORD-1110 | fabric in-house | 2026-05-29 | 2026-05-29 | 0 | Done | Yes
TNA-010-10 | ORD-1110 | bulk cutting start | 2026-05-31 | 2026-06-02 | 2 | Delayed | Yes
TNA-010-11 | ORD-1110 | sewing start | 2026-06-03 | 2026-06-08 | 5 | Delayed | Yes
TNA-010-12 | ORD-1110 | inline QC | 2026-06-07 | 2026-06-05 | -2 | Done | No
TNA-010-13 | ORD-1110 | finishing & pressing | 2026-06-09 |  |  | Open | No
TNA-010-14 | ORD-1110 | final inspection | 2026-06-11 | 2026-06-13 | 2 | Delayed | Yes
TNA-010-15 | ORD-1110 | packing | 2026-06-12 |  |  | Open | No
TNA-010-16 | ORD-1110 | ex-factory | 2026-06-14 |  |  | Open | Yes
TNA-011-01 | ORD-1111 | tech pack freeze | 2026-08-20 | 2026-08-25 | 5 | Delayed | No
TNA-011-02 | ORD-1111 | BOM final approval | 2026-08-23 |  |  | Open | No
TNA-011-03 | ORD-1111 | fabric booking | 2026-08-25 | 2026-08-23 | -2 | Done | No
TNA-011-04 | ORD-1111 | trim booking | 2026-08-27 |  |  | Open | No
TNA-011-05 | ORD-1111 | fit sample sent | 2026-08-31 | 2026-08-31 | 0 | Done | No
TNA-011-06 | ORD-1111 | fit approval | 2026-09-06 | 2026-09-06 | 0 | Done | No
TNA-011-07 | ORD-1111 | size set sample | 2026-09-10 |  |  | Open | No
TNA-011-08 | ORD-1111 | PP sample approval | 2026-09-16 | 2026-09-17 | 1 | Delayed | Yes
TNA-011-09 | ORD-1111 | fabric in-house | 2026-09-18 | 2026-09-17 | -1 | Done | Yes
TNA-011-10 | ORD-1111 | bulk cutting start | 2026-09-20 | 2026-09-25 | 5 | Delayed | Yes
TNA-011-11 | ORD-1111 | sewing start | 2026-09-23 | 2026-09-25 | 2 | Delayed | Yes
TNA-011-12 | ORD-1111 | inline QC | 2026-09-27 | 2026-09-25 | -2 | Done | No
TNA-011-13 | ORD-1111 | finishing & pressing | 2026-09-29 | 2026-09-29 | 0 | Done | No
TNA-011-14 | ORD-1111 | final inspection | 2026-10-01 | 2026-10-01 | 0 | Done | Yes
TNA-011-15 | ORD-1111 | packing | 2026-10-02 |  |  | Open | No
TNA-011-16 | ORD-1111 | ex-factory | 2026-10-04 |  |  | Open | Yes
TNA-012-01 | ORD-1112 | tech pack freeze | 2026-06-19 | 2026-06-20 | 1 | Delayed | No
TNA-012-02 | ORD-1112 | BOM final approval | 2026-06-22 | 2026-06-22 | 0 | Done | No
TNA-012-03 | ORD-1112 | fabric booking | 2026-06-24 | 2026-06-24 | 0 | Done | No
TNA-012-04 | ORD-1112 | trim booking | 2026-06-26 | 2026-06-25 | -1 | Done | No
TNA-012-05 | ORD-1112 | fit sample sent | 2026-06-30 | 2026-06-30 | 0 | Done | No
TNA-012-06 | ORD-1112 | fit approval | 2026-07-06 | 2026-07-07 | 1 | Delayed | No
TNA-012-07 | ORD-1112 | size set sample | 2026-07-10 | 2026-07-15 | 5 | Delayed | No
TNA-012-08 | ORD-1112 | PP sample approval | 2026-07-16 | 2026-07-16 | 0 | Done | Yes
TNA-012-09 | ORD-1112 | fabric in-house | 2026-07-18 | 2026-07-21 | 3 | Delayed | Yes
TNA-012-10 | ORD-1112 | bulk cutting start | 2026-07-20 | 2026-07-19 | -1 | Done | Yes
TNA-012-11 | ORD-1112 | sewing start | 2026-07-23 | 2026-07-23 | 0 | Done | Yes
TNA-012-12 | ORD-1112 | inline QC | 2026-07-27 |  |  | Open | No
TNA-012-13 | ORD-1112 | finishing & pressing | 2026-07-29 |  |  | Open | No
TNA-012-14 | ORD-1112 | final inspection | 2026-07-31 | 2026-08-01 | 1 | Delayed | Yes
TNA-012-15 | ORD-1112 | packing | 2026-08-01 | 2026-08-01 | 0 | Done | No
TNA-012-16 | ORD-1112 | ex-factory | 2026-08-03 |  |  | Open | Yes
TNA-013-01 | ORD-1113 | tech pack freeze | 2026-05-10 | 2026-05-08 | -2 | Done | No
TNA-013-02 | ORD-1113 | BOM final approval | 2026-05-13 |  |  | Open | No
TNA-013-03 | ORD-1113 | fabric booking | 2026-05-15 | 2026-05-15 | 0 | Done | No
TNA-013-04 | ORD-1113 | trim booking | 2026-05-17 | 2026-05-19 | 2 | Delayed | No
TNA-013-05 | ORD-1113 | fit sample sent | 2026-05-21 |  |  | Open | No
TNA-013-06 | ORD-1113 | fit approval | 2026-05-27 | 2026-06-01 | 5 | Delayed | No
TNA-013-07 | ORD-1113 | size set sample | 2026-05-31 | 2026-06-03 | 3 | Delayed | No
TNA-013-08 | ORD-1113 | PP sample approval | 2026-06-06 | 2026-06-06 | 0 | Done | Yes
TNA-013-09 | ORD-1113 | fabric in-house | 2026-06-08 | 2026-06-06 | -2 | Done | Yes
TNA-013-10 | ORD-1113 | bulk cutting start | 2026-06-10 |  |  | Open | Yes
TNA-013-11 | ORD-1113 | sewing start | 2026-06-13 |  |  | Open | Yes
TNA-013-12 | ORD-1113 | inline QC | 2026-06-17 | 2026-06-19 | 2 | Delayed | No
TNA-013-13 | ORD-1113 | finishing & pressing | 2026-06-19 | 2026-06-18 | -1 | Done | No
TNA-013-14 | ORD-1113 | final inspection | 2026-06-21 | 2026-06-21 | 0 | Done | Yes
TNA-013-15 | ORD-1113 | packing | 2026-06-22 |  |  | Open | No
TNA-013-16 | ORD-1113 | ex-factory | 2026-06-24 | 2026-06-23 | -1 | Done | Yes
TNA-014-01 | ORD-1114 | tech pack freeze | 2026-08-12 | 2026-08-15 | 3 | Delayed | No
TNA-014-02 | ORD-1114 | BOM final approval | 2026-08-15 |  |  | Open | No
TNA-014-03 | ORD-1114 | fabric booking | 2026-08-17 | 2026-08-18 | 1 | Delayed | No
TNA-014-04 | ORD-1114 | trim booking | 2026-08-19 | 2026-08-22 | 3 | Delayed | No
TNA-014-05 | ORD-1114 | fit sample sent | 2026-08-23 | 2026-08-25 | 2 | Delayed | No
TNA-014-06 | ORD-1114 | fit approval | 2026-08-29 |  |  | Open | No
TNA-014-07 | ORD-1114 | size set sample | 2026-09-02 | 2026-08-31 | -2 | Done | No
TNA-014-08 | ORD-1114 | PP sample approval | 2026-09-08 | 2026-09-10 | 2 | Delayed | Yes
TNA-014-09 | ORD-1114 | fabric in-house | 2026-09-10 | 2026-09-10 | 0 | Done | Yes
TNA-014-10 | ORD-1114 | bulk cutting start | 2026-09-12 |  |  | Open | Yes
TNA-014-11 | ORD-1114 | sewing start | 2026-09-15 | 2026-09-18 | 3 | Delayed | Yes
TNA-014-12 | ORD-1114 | inline QC | 2026-09-19 |  |  | Open | No
TNA-014-13 | ORD-1114 | finishing & pressing | 2026-09-21 | 2026-09-21 | 0 | Done | No
TNA-014-14 | ORD-1114 | final inspection | 2026-09-23 | 2026-09-26 | 3 | Delayed | Yes
TNA-014-15 | ORD-1114 | packing | 2026-09-24 | 2026-09-29 | 5 | Delayed | No
TNA-014-16 | ORD-1114 | ex-factory | 2026-09-26 | 2026-09-25 | -1 | Done | Yes
TNA-015-01 | ORD-1115 | tech pack freeze | 2026-05-29 | 2026-05-29 | 0 | Done | No
TNA-015-02 | ORD-1115 | BOM final approval | 2026-06-01 | 2026-06-06 | 5 | Delayed | No
TNA-015-03 | ORD-1115 | fabric booking | 2026-06-03 | 2026-06-08 | 5 | Delayed | No
TNA-015-04 | ORD-1115 | trim booking | 2026-06-05 |  |  | Open | No
TNA-015-05 | ORD-1115 | fit sample sent | 2026-06-09 |  |  | Open | No
TNA-015-06 | ORD-1115 | fit approval | 2026-06-15 |  |  | Open | No
TNA-015-07 | ORD-1115 | size set sample | 2026-06-19 | 2026-06-24 | 5 | Delayed | No
TNA-015-08 | ORD-1115 | PP sample approval | 2026-06-25 |  |  | Open | Yes
TNA-015-09 | ORD-1115 | fabric in-house | 2026-06-27 | 2026-07-02 | 5 | Delayed | Yes
TNA-015-10 | ORD-1115 | bulk cutting start | 2026-06-29 | 2026-06-29 | 0 | Done | Yes
TNA-015-11 | ORD-1115 | sewing start | 2026-07-02 | 2026-07-03 | 1 | Delayed | Yes
TNA-015-12 | ORD-1115 | inline QC | 2026-07-06 | 2026-07-04 | -2 | Done | No
TNA-015-13 | ORD-1115 | finishing & pressing | 2026-07-08 |  |  | Open | No
TNA-015-14 | ORD-1115 | final inspection | 2026-07-10 |  |  | Open | Yes
TNA-015-15 | ORD-1115 | packing | 2026-07-11 | 2026-07-14 | 3 | Delayed | No
TNA-015-16 | ORD-1115 | ex-factory | 2026-07-13 | 2026-07-13 | 0 | Done | Yes
TNA-016-01 | ORD-1116 | tech pack freeze | 2026-06-17 |  |  | Open | No
TNA-016-02 | ORD-1116 | BOM final approval | 2026-06-20 | 2026-06-20 | 0 | Done | No
TNA-016-03 | ORD-1116 | fabric booking | 2026-06-22 | 2026-06-20 | -2 | Done | No
TNA-016-04 | ORD-1116 | trim booking | 2026-06-24 |  |  | Open | No
TNA-016-05 | ORD-1116 | fit sample sent | 2026-06-28 |  |  | Open | No
TNA-016-06 | ORD-1116 | fit approval | 2026-07-04 | 2026-07-06 | 2 | Delayed | No
TNA-016-07 | ORD-1116 | size set sample | 2026-07-08 | 2026-07-08 | 0 | Done | No
TNA-016-08 | ORD-1116 | PP sample approval | 2026-07-14 | 2026-07-15 | 1 | Delayed | Yes
TNA-016-09 | ORD-1116 | fabric in-house | 2026-07-16 |  |  | Open | Yes
TNA-016-10 | ORD-1116 | bulk cutting start | 2026-07-18 |  |  | Open | Yes
TNA-016-11 | ORD-1116 | sewing start | 2026-07-21 |  |  | Open | Yes
TNA-016-12 | ORD-1116 | inline QC | 2026-07-25 | 2026-07-26 | 1 | Delayed | No
TNA-016-13 | ORD-1116 | finishing & pressing | 2026-07-27 |  |  | Open | No
TNA-016-14 | ORD-1116 | final inspection | 2026-07-29 | 2026-07-29 | 0 | Done | Yes
TNA-016-15 | ORD-1116 | packing | 2026-07-30 |  |  | Open | No
TNA-016-16 | ORD-1116 | ex-factory | 2026-08-01 |  |  | Open | Yes
TNA-017-01 | ORD-1117 | tech pack freeze | 2026-06-14 |  |  | Open | No
TNA-017-02 | ORD-1117 | BOM final approval | 2026-06-17 | 2026-06-17 | 0 | Done | No
TNA-017-03 | ORD-1117 | fabric booking | 2026-06-19 | 2026-06-18 | -1 | Done | No
TNA-017-04 | ORD-1117 | trim booking | 2026-06-21 | 2026-06-21 | 0 | Done | No
TNA-017-05 | ORD-1117 | fit sample sent | 2026-06-25 | 2026-06-28 | 3 | Delayed | No
TNA-017-06 | ORD-1117 | fit approval | 2026-07-01 | 2026-07-01 | 0 | Done | No
TNA-017-07 | ORD-1117 | size set sample | 2026-07-05 |  |  | Open | No
TNA-017-08 | ORD-1117 | PP sample approval | 2026-07-11 | 2026-07-11 | 0 | Done | Yes
TNA-017-09 | ORD-1117 | fabric in-house | 2026-07-13 |  |  | Open | Yes
TNA-017-10 | ORD-1117 | bulk cutting start | 2026-07-15 |  |  | Open | Yes
TNA-017-11 | ORD-1117 | sewing start | 2026-07-18 | 2026-07-16 | -2 | Done | Yes
TNA-017-12 | ORD-1117 | inline QC | 2026-07-22 | 2026-07-22 | 0 | Done | No
TNA-017-13 | ORD-1117 | finishing & pressing | 2026-07-24 |  |  | Open | No
TNA-017-14 | ORD-1117 | final inspection | 2026-07-26 |  |  | Open | Yes
TNA-017-15 | ORD-1117 | packing | 2026-07-27 |  |  | Open | No
TNA-017-16 | ORD-1117 | ex-factory | 2026-07-29 |  |  | Open | Yes
TNA-018-01 | ORD-1118 | tech pack freeze | 2026-07-25 | 2026-07-27 | 2 | Delayed | No
TNA-018-02 | ORD-1118 | BOM final approval | 2026-07-28 | 2026-07-29 | 1 | Delayed | No
TNA-018-03 | ORD-1118 | fabric booking | 2026-07-30 | 2026-07-30 | 0 | Done | No
TNA-018-04 | ORD-1118 | trim booking | 2026-08-01 |  |  | Open | No
TNA-018-05 | ORD-1118 | fit sample sent | 2026-08-05 |  |  | Open | No
TNA-018-06 | ORD-1118 | fit approval | 2026-08-11 | 2026-08-14 | 3 | Delayed | No
TNA-018-07 | ORD-1118 | size set sample | 2026-08-15 | 2026-08-15 | 0 | Done | No
TNA-018-08 | ORD-1118 | PP sample approval | 2026-08-21 |  |  | Open | Yes
TNA-018-09 | ORD-1118 | fabric in-house | 2026-08-23 | 2026-08-24 | 1 | Delayed | Yes
TNA-018-10 | ORD-1118 | bulk cutting start | 2026-08-25 | 2026-08-25 | 0 | Done | Yes
TNA-018-11 | ORD-1118 | sewing start | 2026-08-28 | 2026-08-28 | 0 | Done | Yes
TNA-018-12 | ORD-1118 | inline QC | 2026-09-01 | 2026-08-30 | -2 | Done | No
TNA-018-13 | ORD-1118 | finishing & pressing | 2026-09-03 |  |  | Open | No
TNA-018-14 | ORD-1118 | final inspection | 2026-09-05 |  |  | Open | Yes
TNA-018-15 | ORD-1118 | packing | 2026-09-06 | 2026-09-04 | -2 | Done | No
TNA-018-16 | ORD-1118 | ex-factory | 2026-09-08 | 2026-09-09 | 1 | Delayed | Yes
TNA-019-01 | ORD-1119 | tech pack freeze | 2026-07-10 |  |  | Open | No
TNA-019-02 | ORD-1119 | BOM final approval | 2026-07-13 |  |  | Open | No
TNA-019-03 | ORD-1119 | fabric booking | 2026-07-15 | 2026-07-14 | -1 | Done | No
TNA-019-04 | ORD-1119 | trim booking | 2026-07-17 |  |  | Open | No
TNA-019-05 | ORD-1119 | fit sample sent | 2026-07-21 | 2026-07-20 | -1 | Done | No
TNA-019-06 | ORD-1119 | fit approval | 2026-07-27 | 2026-07-28 | 1 | Delayed | No
TNA-019-07 | ORD-1119 | size set sample | 2026-07-31 | 2026-07-30 | -1 | Done | No
TNA-019-08 | ORD-1119 | PP sample approval | 2026-08-06 |  |  | Open | Yes
TNA-019-09 | ORD-1119 | fabric in-house | 2026-08-08 |  |  | Open | Yes
TNA-019-10 | ORD-1119 | bulk cutting start | 2026-08-10 |  |  | Open | Yes
TNA-019-11 | ORD-1119 | sewing start | 2026-08-13 | 2026-08-11 | -2 | Done | Yes
TNA-019-12 | ORD-1119 | inline QC | 2026-08-17 | 2026-08-17 | 0 | Done | No
TNA-019-13 | ORD-1119 | finishing & pressing | 2026-08-19 |  |  | Open | No
TNA-019-14 | ORD-1119 | final inspection | 2026-08-21 | 2026-08-20 | -1 | Done | Yes
TNA-019-15 | ORD-1119 | packing | 2026-08-22 |  |  | Open | No
TNA-019-16 | ORD-1119 | ex-factory | 2026-08-24 | 2026-08-27 | 3 | Delayed | Yes
TNA-020-01 | ORD-1120 | tech pack freeze | 2026-05-30 |  |  | Open | No
TNA-020-02 | ORD-1120 | BOM final approval | 2026-06-02 |  |  | Open | No
TNA-020-03 | ORD-1120 | fabric booking | 2026-06-04 |  |  | Open | No
TNA-020-04 | ORD-1120 | trim booking | 2026-06-06 | 2026-06-08 | 2 | Delayed | No
TNA-020-05 | ORD-1120 | fit sample sent | 2026-06-10 | 2026-06-12 | 2 | Delayed | No
TNA-020-06 | ORD-1120 | fit approval | 2026-06-16 | 2026-06-19 | 3 | Delayed | No
TNA-020-07 | ORD-1120 | size set sample | 2026-06-20 |  |  | Open | No
TNA-020-08 | ORD-1120 | PP sample approval | 2026-06-26 | 2026-06-26 | 0 | Done | Yes
TNA-020-09 | ORD-1120 | fabric in-house | 2026-06-28 | 2026-06-27 | -1 | Done | Yes
TNA-020-10 | ORD-1120 | bulk cutting start | 2026-06-30 |  |  | Open | Yes
TNA-020-11 | ORD-1120 | sewing start | 2026-07-03 | 2026-07-01 | -2 | Done | Yes
TNA-020-12 | ORD-1120 | inline QC | 2026-07-07 | 2026-07-06 | -1 | Done | No
TNA-020-13 | ORD-1120 | finishing & pressing | 2026-07-09 | 2026-07-09 | 0 | Done | No
TNA-020-14 | ORD-1120 | final inspection | 2026-07-11 |  |  | Open | Yes
TNA-020-15 | ORD-1120 | packing | 2026-07-12 | 2026-07-11 | -1 | Done | No
TNA-020-16 | ORD-1120 | ex-factory | 2026-07-14 | 2026-07-13 | -1 | Done | Yes
TNA-021-01 | ORD-1121 | tech pack freeze | 2026-07-29 | 2026-08-01 | 3 | Delayed | No
TNA-021-02 | ORD-1121 | BOM final approval | 2026-08-01 |  |  | Open | No
TNA-021-03 | ORD-1121 | fabric booking | 2026-08-03 | 2026-08-03 | 0 | Done | No
TNA-021-04 | ORD-1121 | trim booking | 2026-08-05 | 2026-08-07 | 2 | Delayed | No
TNA-021-05 | ORD-1121 | fit sample sent | 2026-08-09 | 2026-08-08 | -1 | Done | No
TNA-021-06 | ORD-1121 | fit approval | 2026-08-15 | 2026-08-15 | 0 | Done | No
TNA-021-07 | ORD-1121 | size set sample | 2026-08-19 | 2026-08-24 | 5 | Delayed | No
TNA-021-08 | ORD-1121 | PP sample approval | 2026-08-25 |  |  | Open | Yes
TNA-021-09 | ORD-1121 | fabric in-house | 2026-08-27 |  |  | Open | Yes
TNA-021-10 | ORD-1121 | bulk cutting start | 2026-08-29 | 2026-08-29 | 0 | Done | Yes
TNA-021-11 | ORD-1121 | sewing start | 2026-09-01 | 2026-08-31 | -1 | Done | Yes
TNA-021-12 | ORD-1121 | inline QC | 2026-09-05 | 2026-09-10 | 5 | Delayed | No
TNA-021-13 | ORD-1121 | finishing & pressing | 2026-09-07 |  |  | Open | No
TNA-021-14 | ORD-1121 | final inspection | 2026-09-09 | 2026-09-10 | 1 | Delayed | Yes
TNA-021-15 | ORD-1121 | packing | 2026-09-10 | 2026-09-09 | -1 | Done | No
TNA-021-16 | ORD-1121 | ex-factory | 2026-09-12 | 2026-09-15 | 3 | Delayed | Yes
TNA-022-01 | ORD-1122 | tech pack freeze | 2026-05-18 | 2026-05-16 | -2 | Done | No
TNA-022-02 | ORD-1122 | BOM final approval | 2026-05-21 | 2026-05-21 | 0 | Done | No
TNA-022-03 | ORD-1122 | fabric booking | 2026-05-23 |  |  | Open | No
TNA-022-04 | ORD-1122 | trim booking | 2026-05-25 | 2026-05-24 | -1 | Done | No
TNA-022-05 | ORD-1122 | fit sample sent | 2026-05-29 | 2026-05-31 | 2 | Delayed | No
TNA-022-06 | ORD-1122 | fit approval | 2026-06-04 | 2026-06-04 | 0 | Done | No
TNA-022-07 | ORD-1122 | size set sample | 2026-06-08 | 2026-06-13 | 5 | Delayed | No
TNA-022-08 | ORD-1122 | PP sample approval | 2026-06-14 | 2026-06-15 | 1 | Delayed | Yes
TNA-022-09 | ORD-1122 | fabric in-house | 2026-06-16 |  |  | Open | Yes
TNA-022-10 | ORD-1122 | bulk cutting start | 2026-06-18 | 2026-06-21 | 3 | Delayed | Yes
TNA-022-11 | ORD-1122 | sewing start | 2026-06-21 | 2026-06-24 | 3 | Delayed | Yes
TNA-022-12 | ORD-1122 | inline QC | 2026-06-25 | 2026-06-25 | 0 | Done | No
TNA-022-13 | ORD-1122 | finishing & pressing | 2026-06-27 |  |  | Open | No
TNA-022-14 | ORD-1122 | final inspection | 2026-06-29 | 2026-06-29 | 0 | Done | Yes
TNA-022-15 | ORD-1122 | packing | 2026-06-30 |  |  | Open | No
TNA-022-16 | ORD-1122 | ex-factory | 2026-07-02 |  |  | Open | Yes
TNA-023-01 | ORD-1123 | tech pack freeze | 2026-07-05 | 2026-07-06 | 1 | Delayed | No
TNA-023-02 | ORD-1123 | BOM final approval | 2026-07-08 |  |  | Open | No
TNA-023-03 | ORD-1123 | fabric booking | 2026-07-10 | 2026-07-10 | 0 | Done | No
TNA-023-04 | ORD-1123 | trim booking | 2026-07-12 | 2026-07-14 | 2 | Delayed | No
TNA-023-05 | ORD-1123 | fit sample sent | 2026-07-16 |  |  | Open | No
TNA-023-06 | ORD-1123 | fit approval | 2026-07-22 | 2026-07-27 | 5 | Delayed | No
TNA-023-07 | ORD-1123 | size set sample | 2026-07-26 |  |  | Open | No
TNA-023-08 | ORD-1123 | PP sample approval | 2026-08-01 |  |  | Open | Yes
TNA-023-09 | ORD-1123 | fabric in-house | 2026-08-03 | 2026-08-03 | 0 | Done | Yes
TNA-023-10 | ORD-1123 | bulk cutting start | 2026-08-05 | 2026-08-04 | -1 | Done | Yes
TNA-023-11 | ORD-1123 | sewing start | 2026-08-08 | 2026-08-06 | -2 | Done | Yes
TNA-023-12 | ORD-1123 | inline QC | 2026-08-12 | 2026-08-17 | 5 | Delayed | No
TNA-023-13 | ORD-1123 | finishing & pressing | 2026-08-14 |  |  | Open | No
TNA-023-14 | ORD-1123 | final inspection | 2026-08-16 |  |  | Open | Yes
TNA-023-15 | ORD-1123 | packing | 2026-08-17 | 2026-08-16 | -1 | Done | No
TNA-023-16 | ORD-1123 | ex-factory | 2026-08-19 |  |  | Open | Yes
TNA-024-01 | ORD-1124 | tech pack freeze | 2026-09-07 | 2026-09-07 | 0 | Done | No
TNA-024-02 | ORD-1124 | BOM final approval | 2026-09-10 |  |  | Open | No
TNA-024-03 | ORD-1124 | fabric booking | 2026-09-12 |  |  | Open | No
TNA-024-04 | ORD-1124 | trim booking | 2026-09-14 | 2026-09-16 | 2 | Delayed | No
TNA-024-05 | ORD-1124 | fit sample sent | 2026-09-18 | 2026-09-20 | 2 | Delayed | No
TNA-024-06 | ORD-1124 | fit approval | 2026-09-24 | 2026-09-24 | 0 | Done | No
TNA-024-07 | ORD-1124 | size set sample | 2026-09-28 |  |  | Open | No
TNA-024-08 | ORD-1124 | PP sample approval | 2026-10-04 | 2026-10-03 | -1 | Done | Yes
TNA-024-09 | ORD-1124 | fabric in-house | 2026-10-06 | 2026-10-11 | 5 | Delayed | Yes
TNA-024-10 | ORD-1124 | bulk cutting start | 2026-10-08 | 2026-10-09 | 1 | Delayed | Yes
TNA-024-11 | ORD-1124 | sewing start | 2026-10-11 |  |  | Open | Yes
TNA-024-12 | ORD-1124 | inline QC | 2026-10-15 | 2026-10-13 | -2 | Done | No
TNA-024-13 | ORD-1124 | finishing & pressing | 2026-10-17 |  |  | Open | No
TNA-024-14 | ORD-1124 | final inspection | 2026-10-19 | 2026-10-24 | 5 | Delayed | Yes
TNA-024-15 | ORD-1124 | packing | 2026-10-20 |  |  | Open | No
TNA-024-16 | ORD-1124 | ex-factory | 2026-10-22 | 2026-10-22 | 0 | Done | Yes
TNA-025-01 | ORD-1125 | tech pack freeze | 2026-07-27 | 2026-07-26 | -1 | Done | No
TNA-025-02 | ORD-1125 | BOM final approval | 2026-07-30 |  |  | Open | No
TNA-025-03 | ORD-1125 | fabric booking | 2026-08-01 | 2026-07-31 | -1 | Done | No
TNA-025-04 | ORD-1125 | trim booking | 2026-08-03 |  |  | Open | No
TNA-025-05 | ORD-1125 | fit sample sent | 2026-08-07 |  |  | Open | No
TNA-025-06 | ORD-1125 | fit approval | 2026-08-13 |  |  | Open | No
TNA-025-07 | ORD-1125 | size set sample | 2026-08-17 |  |  | Open | No
TNA-025-08 | ORD-1125 | PP sample approval | 2026-08-23 | 2026-08-26 | 3 | Delayed | Yes
TNA-025-09 | ORD-1125 | fabric in-house | 2026-08-25 | 2026-08-28 | 3 | Delayed | Yes
TNA-025-10 | ORD-1125 | bulk cutting start | 2026-08-27 | 2026-08-27 | 0 | Done | Yes
TNA-025-11 | ORD-1125 | sewing start | 2026-08-30 | 2026-09-01 | 2 | Delayed | Yes
TNA-025-12 | ORD-1125 | inline QC | 2026-09-03 | 2026-09-04 | 1 | Delayed | No
TNA-025-13 | ORD-1125 | finishing & pressing | 2026-09-05 |  |  | Open | No
TNA-025-14 | ORD-1125 | final inspection | 2026-09-07 | 2026-09-10 | 3 | Delayed | Yes
TNA-025-15 | ORD-1125 | packing | 2026-09-08 |  |  | Open | No
TNA-025-16 | ORD-1125 | ex-factory | 2026-09-10 |  |  | Open | Yes
TNA-026-01 | ORD-1126 | tech pack freeze | 2026-05-22 | 2026-05-22 | 0 | Done | No
TNA-026-02 | ORD-1126 | BOM final approval | 2026-05-25 | 2026-05-28 | 3 | Delayed | No
TNA-026-03 | ORD-1126 | fabric booking | 2026-05-27 |  |  | Open | No
TNA-026-04 | ORD-1126 | trim booking | 2026-05-29 |  |  | Open | No
TNA-026-05 | ORD-1126 | fit sample sent | 2026-06-02 |  |  | Open | No
TNA-026-06 | ORD-1126 | fit approval | 2026-06-08 | 2026-06-08 | 0 | Done | No
TNA-026-07 | ORD-1126 | size set sample | 2026-06-12 |  |  | Open | No
TNA-026-08 | ORD-1126 | PP sample approval | 2026-06-18 | 2026-06-19 | 1 | Delayed | Yes
TNA-026-09 | ORD-1126 | fabric in-house | 2026-06-20 | 2026-06-22 | 2 | Delayed | Yes
TNA-026-10 | ORD-1126 | bulk cutting start | 2026-06-22 | 2026-06-21 | -1 | Done | Yes
TNA-026-11 | ORD-1126 | sewing start | 2026-06-25 | 2026-06-25 | 0 | Done | Yes
TNA-026-12 | ORD-1126 | inline QC | 2026-06-29 |  |  | Open | No
TNA-026-13 | ORD-1126 | finishing & pressing | 2026-07-01 | 2026-07-04 | 3 | Delayed | No
TNA-026-14 | ORD-1126 | final inspection | 2026-07-03 |  |  | Open | Yes
TNA-026-15 | ORD-1126 | packing | 2026-07-04 |  |  | Open | No
TNA-026-16 | ORD-1126 | ex-factory | 2026-07-06 |  |  | Open | Yes
TNA-027-01 | ORD-1127 | tech pack freeze | 2026-07-21 | 2026-07-21 | 0 | Done | No
TNA-027-02 | ORD-1127 | BOM final approval | 2026-07-24 | 2026-07-29 | 5 | Delayed | No
TNA-027-03 | ORD-1127 | fabric booking | 2026-07-26 | 2026-07-31 | 5 | Delayed | No
TNA-027-04 | ORD-1127 | trim booking | 2026-07-28 |  |  | Open | No
TNA-027-05 | ORD-1127 | fit sample sent | 2026-08-01 | 2026-08-01 | 0 | Done | No
TNA-027-06 | ORD-1127 | fit approval | 2026-08-07 |  |  | Open | No
TNA-027-07 | ORD-1127 | size set sample | 2026-08-11 | 2026-08-09 | -2 | Done | No
TNA-027-08 | ORD-1127 | PP sample approval | 2026-08-17 | 2026-08-20 | 3 | Delayed | Yes
TNA-027-09 | ORD-1127 | fabric in-house | 2026-08-19 | 2026-08-20 | 1 | Delayed | Yes
TNA-027-10 | ORD-1127 | bulk cutting start | 2026-08-21 |  |  | Open | Yes
TNA-027-11 | ORD-1127 | sewing start | 2026-08-24 | 2026-08-27 | 3 | Delayed | Yes
TNA-027-12 | ORD-1127 | inline QC | 2026-08-28 | 2026-08-27 | -1 | Done | No
TNA-027-13 | ORD-1127 | finishing & pressing | 2026-08-30 |  |  | Open | No
TNA-027-14 | ORD-1127 | final inspection | 2026-09-01 | 2026-09-04 | 3 | Delayed | Yes
TNA-027-15 | ORD-1127 | packing | 2026-09-02 | 2026-09-02 | 0 | Done | No
TNA-027-16 | ORD-1127 | ex-factory | 2026-09-04 |  |  | Open | Yes
TNA-028-01 | ORD-1128 | tech pack freeze | 2026-05-26 | 2026-05-31 | 5 | Delayed | No
TNA-028-02 | ORD-1128 | BOM final approval | 2026-05-29 | 2026-05-29 | 0 | Done | No
TNA-028-03 | ORD-1128 | fabric booking | 2026-05-31 |  |  | Open | No
TNA-028-04 | ORD-1128 | trim booking | 2026-06-02 | 2026-06-01 | -1 | Done | No
TNA-028-05 | ORD-1128 | fit sample sent | 2026-06-06 | 2026-06-08 | 2 | Delayed | No
TNA-028-06 | ORD-1128 | fit approval | 2026-06-12 | 2026-06-12 | 0 | Done | No
TNA-028-07 | ORD-1128 | size set sample | 2026-06-16 |  |  | Open | No
TNA-028-08 | ORD-1128 | PP sample approval | 2026-06-22 | 2026-06-22 | 0 | Done | Yes
TNA-028-09 | ORD-1128 | fabric in-house | 2026-06-24 | 2026-06-26 | 2 | Delayed | Yes
TNA-028-10 | ORD-1128 | bulk cutting start | 2026-06-26 | 2026-06-24 | -2 | Done | Yes
TNA-028-11 | ORD-1128 | sewing start | 2026-06-29 | 2026-06-29 | 0 | Done | Yes
TNA-028-12 | ORD-1128 | inline QC | 2026-07-03 | 2026-07-01 | -2 | Done | No
TNA-028-13 | ORD-1128 | finishing & pressing | 2026-07-05 | 2026-07-05 | 0 | Done | No
TNA-028-14 | ORD-1128 | final inspection | 2026-07-07 |  |  | Open | Yes
TNA-028-15 | ORD-1128 | packing | 2026-07-08 |  |  | Open | No
TNA-028-16 | ORD-1128 | ex-factory | 2026-07-10 | 2026-07-12 | 2 | Delayed | Yes
TNA-029-01 | ORD-1129 | tech pack freeze | 2026-06-23 |  |  | Open | No
TNA-029-02 | ORD-1129 | BOM final approval | 2026-06-26 | 2026-06-26 | 0 | Done | No
TNA-029-03 | ORD-1129 | fabric booking | 2026-06-28 | 2026-07-03 | 5 | Delayed | No
TNA-029-04 | ORD-1129 | trim booking | 2026-06-30 |  |  | Open | No
TNA-029-05 | ORD-1129 | fit sample sent | 2026-07-04 | 2026-07-03 | -1 | Done | No
TNA-029-06 | ORD-1129 | fit approval | 2026-07-10 | 2026-07-11 | 1 | Delayed | No
TNA-029-07 | ORD-1129 | size set sample | 2026-07-14 | 2026-07-14 | 0 | Done | No
TNA-029-08 | ORD-1129 | PP sample approval | 2026-07-20 | 2026-07-19 | -1 | Done | Yes
TNA-029-09 | ORD-1129 | fabric in-house | 2026-07-22 | 2026-07-23 | 1 | Delayed | Yes
TNA-029-10 | ORD-1129 | bulk cutting start | 2026-07-24 |  |  | Open | Yes
TNA-029-11 | ORD-1129 | sewing start | 2026-07-27 | 2026-07-27 | 0 | Done | Yes
TNA-029-12 | ORD-1129 | inline QC | 2026-07-31 | 2026-07-31 | 0 | Done | No
TNA-029-13 | ORD-1129 | finishing & pressing | 2026-08-02 | 2026-08-07 | 5 | Delayed | No
TNA-029-14 | ORD-1129 | final inspection | 2026-08-04 |  |  | Open | Yes
TNA-029-15 | ORD-1129 | packing | 2026-08-05 |  |  | Open | No
TNA-029-16 | ORD-1129 | ex-factory | 2026-08-07 |  |  | Open | Yes
TNA-030-01 | ORD-1130 | tech pack freeze | 2026-08-26 |  |  | Open | No
TNA-030-02 | ORD-1130 | BOM final approval | 2026-08-29 | 2026-08-30 | 1 | Delayed | No
TNA-030-03 | ORD-1130 | fabric booking | 2026-08-31 |  |  | Open | No
TNA-030-04 | ORD-1130 | trim booking | 2026-09-02 |  |  | Open | No
TNA-030-05 | ORD-1130 | fit sample sent | 2026-09-06 |  |  | Open | No
TNA-030-06 | ORD-1130 | fit approval | 2026-09-12 |  |  | Open | No
TNA-030-07 | ORD-1130 | size set sample | 2026-09-16 | 2026-09-18 | 2 | Delayed | No
TNA-030-08 | ORD-1130 | PP sample approval | 2026-09-22 | 2026-09-20 | -2 | Done | Yes
TNA-030-09 | ORD-1130 | fabric in-house | 2026-09-24 | 2026-09-24 | 0 | Done | Yes
TNA-030-10 | ORD-1130 | bulk cutting start | 2026-09-26 | 2026-09-26 | 0 | Done | Yes
TNA-030-11 | ORD-1130 | sewing start | 2026-09-29 |  |  | Open | Yes
TNA-030-12 | ORD-1130 | inline QC | 2026-10-03 | 2026-10-06 | 3 | Delayed | No
TNA-030-13 | ORD-1130 | finishing & pressing | 2026-10-05 |  |  | Open | No
TNA-030-14 | ORD-1130 | final inspection | 2026-10-07 |  |  | Open | Yes
TNA-030-15 | ORD-1130 | packing | 2026-10-08 | 2026-10-08 | 0 | Done | No
TNA-030-16 | ORD-1130 | ex-factory | 2026-10-10 |  |  | Open | Yes
TNA-031-01 | ORD-1131 | tech pack freeze | 2026-05-22 |  |  | Open | No
TNA-031-02 | ORD-1131 | BOM final approval | 2026-05-25 | 2026-05-24 | -1 | Done | No
TNA-031-03 | ORD-1131 | fabric booking | 2026-05-27 | 2026-05-27 | 0 | Done | No
TNA-031-04 | ORD-1131 | trim booking | 2026-05-29 |  |  | Open | No
TNA-031-05 | ORD-1131 | fit sample sent | 2026-06-02 | 2026-06-02 | 0 | Done | No
TNA-031-06 | ORD-1131 | fit approval | 2026-06-08 |  |  | Open | No
TNA-031-07 | ORD-1131 | size set sample | 2026-06-12 |  |  | Open | No
TNA-031-08 | ORD-1131 | PP sample approval | 2026-06-18 |  |  | Open | Yes
TNA-031-09 | ORD-1131 | fabric in-house | 2026-06-20 | 2026-06-20 | 0 | Done | Yes
TNA-031-10 | ORD-1131 | bulk cutting start | 2026-06-22 |  |  | Open | Yes
TNA-031-11 | ORD-1131 | sewing start | 2026-06-25 | 2026-06-26 | 1 | Delayed | Yes
TNA-031-12 | ORD-1131 | inline QC | 2026-06-29 | 2026-06-29 | 0 | Done | No
TNA-031-13 | ORD-1131 | finishing & pressing | 2026-07-01 | 2026-06-30 | -1 | Done | No
TNA-031-14 | ORD-1131 | final inspection | 2026-07-03 | 2026-07-02 | -1 | Done | Yes
TNA-031-15 | ORD-1131 | packing | 2026-07-04 | 2026-07-04 | 0 | Done | No
TNA-031-16 | ORD-1131 | ex-factory | 2026-07-06 | 2026-07-08 | 2 | Delayed | Yes
TNA-032-01 | ORD-1132 | tech pack freeze | 2026-07-09 | 2026-07-11 | 2 | Delayed | No
TNA-032-02 | ORD-1132 | BOM final approval | 2026-07-12 | 2026-07-12 | 0 | Done | No
TNA-032-03 | ORD-1132 | fabric booking | 2026-07-14 | 2026-07-14 | 0 | Done | No
TNA-032-04 | ORD-1132 | trim booking | 2026-07-16 | 2026-07-19 | 3 | Delayed | No
TNA-032-05 | ORD-1132 | fit sample sent | 2026-07-20 | 2026-07-20 | 0 | Done | No
TNA-032-06 | ORD-1132 | fit approval | 2026-07-26 |  |  | Open | No
TNA-032-07 | ORD-1132 | size set sample | 2026-07-30 | 2026-07-30 | 0 | Done | No
TNA-032-08 | ORD-1132 | PP sample approval | 2026-08-05 | 2026-08-03 | -2 | Done | Yes
TNA-032-09 | ORD-1132 | fabric in-house | 2026-08-07 | 2026-08-07 | 0 | Done | Yes
TNA-032-10 | ORD-1132 | bulk cutting start | 2026-08-09 | 2026-08-09 | 0 | Done | Yes
TNA-032-11 | ORD-1132 | sewing start | 2026-08-12 | 2026-08-12 | 0 | Done | Yes
TNA-032-12 | ORD-1132 | inline QC | 2026-08-16 | 2026-08-15 | -1 | Done | No
TNA-032-13 | ORD-1132 | finishing & pressing | 2026-08-18 | 2026-08-20 | 2 | Delayed | No
TNA-032-14 | ORD-1132 | final inspection | 2026-08-20 | 2026-08-22 | 2 | Delayed | Yes
TNA-032-15 | ORD-1132 | packing | 2026-08-21 | 2026-08-24 | 3 | Delayed | No
TNA-032-16 | ORD-1132 | ex-factory | 2026-08-23 | 2026-08-21 | -2 | Done | Yes
TNA-033-01 | ORD-1133 | tech pack freeze | 2026-06-27 | 2026-06-28 | 1 | Delayed | No
TNA-033-02 | ORD-1133 | BOM final approval | 2026-06-30 |  |  | Open | No
TNA-033-03 | ORD-1133 | fabric booking | 2026-07-02 |  |  | Open | No
TNA-033-04 | ORD-1133 | trim booking | 2026-07-04 |  |  | Open | No
TNA-033-05 | ORD-1133 | fit sample sent | 2026-07-08 | 2026-07-06 | -2 | Done | No
TNA-033-06 | ORD-1133 | fit approval | 2026-07-14 |  |  | Open | No
TNA-033-07 | ORD-1133 | size set sample | 2026-07-18 | 2026-07-18 | 0 | Done | No
TNA-033-08 | ORD-1133 | PP sample approval | 2026-07-24 | 2026-07-25 | 1 | Delayed | Yes
TNA-033-09 | ORD-1133 | fabric in-house | 2026-07-26 | 2026-07-25 | -1 | Done | Yes
TNA-033-10 | ORD-1133 | bulk cutting start | 2026-07-28 | 2026-07-28 | 0 | Done | Yes
TNA-033-11 | ORD-1133 | sewing start | 2026-07-31 | 2026-07-29 | -2 | Done | Yes
TNA-033-12 | ORD-1133 | inline QC | 2026-08-04 | 2026-08-04 | 0 | Done | No
TNA-033-13 | ORD-1133 | finishing & pressing | 2026-08-06 | 2026-08-11 | 5 | Delayed | No
TNA-033-14 | ORD-1133 | final inspection | 2026-08-08 | 2026-08-09 | 1 | Delayed | Yes
TNA-033-15 | ORD-1133 | packing | 2026-08-09 | 2026-08-09 | 0 | Done | No
TNA-033-16 | ORD-1133 | ex-factory | 2026-08-11 | 2026-08-14 | 3 | Delayed | Yes
TNA-034-01 | ORD-1134 | tech pack freeze | 2026-07-04 | 2026-07-04 | 0 | Done | No
TNA-034-02 | ORD-1134 | BOM final approval | 2026-07-07 | 2026-07-09 | 2 | Delayed | No
TNA-034-03 | ORD-1134 | fabric booking | 2026-07-09 | 2026-07-09 | 0 | Done | No
TNA-034-04 | ORD-1134 | trim booking | 2026-07-11 |  |  | Open | No
TNA-034-05 | ORD-1134 | fit sample sent | 2026-07-15 | 2026-07-13 | -2 | Done | No
TNA-034-06 | ORD-1134 | fit approval | 2026-07-21 | 2026-07-21 | 0 | Done | No
TNA-034-07 | ORD-1134 | size set sample | 2026-07-25 | 2026-07-23 | -2 | Done | No
TNA-034-08 | ORD-1134 | PP sample approval | 2026-07-31 | 2026-07-31 | 0 | Done | Yes
TNA-034-09 | ORD-1134 | fabric in-house | 2026-08-02 |  |  | Open | Yes
TNA-034-10 | ORD-1134 | bulk cutting start | 2026-08-04 | 2026-08-02 | -2 | Done | Yes
TNA-034-11 | ORD-1134 | sewing start | 2026-08-07 |  |  | Open | Yes
TNA-034-12 | ORD-1134 | inline QC | 2026-08-11 |  |  | Open | No
TNA-034-13 | ORD-1134 | finishing & pressing | 2026-08-13 | 2026-08-12 | -1 | Done | No
TNA-034-14 | ORD-1134 | final inspection | 2026-08-15 | 2026-08-17 | 2 | Delayed | Yes
TNA-034-15 | ORD-1134 | packing | 2026-08-16 | 2026-08-16 | 0 | Done | No
TNA-034-16 | ORD-1134 | ex-factory | 2026-08-18 | 2026-08-18 | 0 | Done | Yes
TNA-035-01 | ORD-1135 | tech pack freeze | 2026-05-27 | 2026-05-25 | -2 | Done | No
TNA-035-02 | ORD-1135 | BOM final approval | 2026-05-30 | 2026-05-29 | -1 | Done | No
TNA-035-03 | ORD-1135 | fabric booking | 2026-06-01 |  |  | Open | No
TNA-035-04 | ORD-1135 | trim booking | 2026-06-03 | 2026-06-03 | 0 | Done | No
TNA-035-05 | ORD-1135 | fit sample sent | 2026-06-07 | 2026-06-06 | -1 | Done | No
TNA-035-06 | ORD-1135 | fit approval | 2026-06-13 | 2026-06-12 | -1 | Done | No
TNA-035-07 | ORD-1135 | size set sample | 2026-06-17 | 2026-06-16 | -1 | Done | No
TNA-035-08 | ORD-1135 | PP sample approval | 2026-06-23 | 2026-06-23 | 0 | Done | Yes
TNA-035-09 | ORD-1135 | fabric in-house | 2026-06-25 |  |  | Open | Yes
TNA-035-10 | ORD-1135 | bulk cutting start | 2026-06-27 |  |  | Open | Yes
TNA-035-11 | ORD-1135 | sewing start | 2026-06-30 |  |  | Open | Yes
TNA-035-12 | ORD-1135 | inline QC | 2026-07-04 | 2026-07-06 | 2 | Delayed | No
TNA-035-13 | ORD-1135 | finishing & pressing | 2026-07-06 | 2026-07-04 | -2 | Done | No
TNA-035-14 | ORD-1135 | final inspection | 2026-07-08 | 2026-07-08 | 0 | Done | Yes
TNA-035-15 | ORD-1135 | packing | 2026-07-09 |  |  | Open | No
TNA-035-16 | ORD-1135 | ex-factory | 2026-07-11 | 2026-07-11 | 0 | Done | Yes
TNA-036-01 | ORD-1136 | tech pack freeze | 2026-06-11 | 2026-06-10 | -1 | Done | No
TNA-036-02 | ORD-1136 | BOM final approval | 2026-06-14 |  |  | Open | No
TNA-036-03 | ORD-1136 | fabric booking | 2026-06-16 |  |  | Open | No
TNA-036-04 | ORD-1136 | trim booking | 2026-06-18 |  |  | Open | No
TNA-036-05 | ORD-1136 | fit sample sent | 2026-06-22 | 2026-06-21 | -1 | Done | No
TNA-036-06 | ORD-1136 | fit approval | 2026-06-28 |  |  | Open | No
TNA-036-07 | ORD-1136 | size set sample | 2026-07-02 | 2026-07-01 | -1 | Done | No
TNA-036-08 | ORD-1136 | PP sample approval | 2026-07-08 |  |  | Open | Yes
TNA-036-09 | ORD-1136 | fabric in-house | 2026-07-10 | 2026-07-13 | 3 | Delayed | Yes
TNA-036-10 | ORD-1136 | bulk cutting start | 2026-07-12 |  |  | Open | Yes
TNA-036-11 | ORD-1136 | sewing start | 2026-07-15 | 2026-07-18 | 3 | Delayed | Yes
TNA-036-12 | ORD-1136 | inline QC | 2026-07-19 | 2026-07-19 | 0 | Done | No
TNA-036-13 | ORD-1136 | finishing & pressing | 2026-07-21 |  |  | Open | No
TNA-036-14 | ORD-1136 | final inspection | 2026-07-23 |  |  | Open | Yes
TNA-036-15 | ORD-1136 | packing | 2026-07-24 | 2026-07-25 | 1 | Delayed | No
TNA-036-16 | ORD-1136 | ex-factory | 2026-07-26 | 2026-07-25 | -1 | Done | Yes
TNA-037-01 | ORD-1137 | tech pack freeze | 2026-05-24 | 2026-05-22 | -2 | Done | No
TNA-037-02 | ORD-1137 | BOM final approval | 2026-05-27 | 2026-05-27 | 0 | Done | No
TNA-037-03 | ORD-1137 | fabric booking | 2026-05-29 |  |  | Open | No
TNA-037-04 | ORD-1137 | trim booking | 2026-05-31 | 2026-06-01 | 1 | Delayed | No
TNA-037-05 | ORD-1137 | fit sample sent | 2026-06-04 |  |  | Open | No
TNA-037-06 | ORD-1137 | fit approval | 2026-06-10 |  |  | Open | No
TNA-037-07 | ORD-1137 | size set sample | 2026-06-14 | 2026-06-13 | -1 | Done | No
TNA-037-08 | ORD-1137 | PP sample approval | 2026-06-20 | 2026-06-21 | 1 | Delayed | Yes
TNA-037-09 | ORD-1137 | fabric in-house | 2026-06-22 | 2026-06-24 | 2 | Delayed | Yes
TNA-037-10 | ORD-1137 | bulk cutting start | 2026-06-24 | 2026-06-27 | 3 | Delayed | Yes
TNA-037-11 | ORD-1137 | sewing start | 2026-06-27 | 2026-06-29 | 2 | Delayed | Yes
TNA-037-12 | ORD-1137 | inline QC | 2026-07-01 |  |  | Open | No
TNA-037-13 | ORD-1137 | finishing & pressing | 2026-07-03 | 2026-07-05 | 2 | Delayed | No
TNA-037-14 | ORD-1137 | final inspection | 2026-07-05 | 2026-07-05 | 0 | Done | Yes
TNA-037-15 | ORD-1137 | packing | 2026-07-06 | 2026-07-04 | -2 | Done | No
TNA-037-16 | ORD-1137 | ex-factory | 2026-07-08 |  |  | Open | Yes
TNA-038-01 | ORD-1138 | tech pack freeze | 2026-05-02 |  |  | Open | No
TNA-038-02 | ORD-1138 | BOM final approval | 2026-05-05 | 2026-05-08 | 3 | Delayed | No
TNA-038-03 | ORD-1138 | fabric booking | 2026-05-07 |  |  | Open | No
TNA-038-04 | ORD-1138 | trim booking | 2026-05-09 |  |  | Open | No
TNA-038-05 | ORD-1138 | fit sample sent | 2026-05-13 | 2026-05-15 | 2 | Delayed | No
TNA-038-06 | ORD-1138 | fit approval | 2026-05-19 |  |  | Open | No
TNA-038-07 | ORD-1138 | size set sample | 2026-05-23 | 2026-05-23 | 0 | Done | No
TNA-038-08 | ORD-1138 | PP sample approval | 2026-05-29 | 2026-06-01 | 3 | Delayed | Yes
TNA-038-09 | ORD-1138 | fabric in-house | 2026-05-31 | 2026-06-02 | 2 | Delayed | Yes
TNA-038-10 | ORD-1138 | bulk cutting start | 2026-06-02 | 2026-06-01 | -1 | Done | Yes
TNA-038-11 | ORD-1138 | sewing start | 2026-06-05 | 2026-06-06 | 1 | Delayed | Yes
TNA-038-12 | ORD-1138 | inline QC | 2026-06-09 | 2026-06-14 | 5 | Delayed | No
TNA-038-13 | ORD-1138 | finishing & pressing | 2026-06-11 |  |  | Open | No
TNA-038-14 | ORD-1138 | final inspection | 2026-06-13 | 2026-06-13 | 0 | Done | Yes
TNA-038-15 | ORD-1138 | packing | 2026-06-14 |  |  | Open | No
TNA-038-16 | ORD-1138 | ex-factory | 2026-06-16 |  |  | Open | Yes
TNA-039-01 | ORD-1139 | tech pack freeze | 2026-07-25 | 2026-07-30 | 5 | Delayed | No
TNA-039-02 | ORD-1139 | BOM final approval | 2026-07-28 |  |  | Open | No
TNA-039-03 | ORD-1139 | fabric booking | 2026-07-30 | 2026-08-01 | 2 | Delayed | No
TNA-039-04 | ORD-1139 | trim booking | 2026-08-01 |  |  | Open | No
TNA-039-05 | ORD-1139 | fit sample sent | 2026-08-05 | 2026-08-06 | 1 | Delayed | No
TNA-039-06 | ORD-1139 | fit approval | 2026-08-11 |  |  | Open | No
TNA-039-07 | ORD-1139 | size set sample | 2026-08-15 | 2026-08-15 | 0 | Done | No
TNA-039-08 | ORD-1139 | PP sample approval | 2026-08-21 |  |  | Open | Yes
TNA-039-09 | ORD-1139 | fabric in-house | 2026-08-23 | 2026-08-21 | -2 | Done | Yes
TNA-039-10 | ORD-1139 | bulk cutting start | 2026-08-25 | 2026-08-25 | 0 | Done | Yes
TNA-039-11 | ORD-1139 | sewing start | 2026-08-28 | 2026-08-31 | 3 | Delayed | Yes
TNA-039-12 | ORD-1139 | inline QC | 2026-09-01 |  |  | Open | No
TNA-039-13 | ORD-1139 | finishing & pressing | 2026-09-03 |  |  | Open | No
TNA-039-14 | ORD-1139 | final inspection | 2026-09-05 | 2026-09-08 | 3 | Delayed | Yes
TNA-039-15 | ORD-1139 | packing | 2026-09-06 | 2026-09-07 | 1 | Delayed | No
TNA-039-16 | ORD-1139 | ex-factory | 2026-09-08 |  |  | Open | Yes
TNA-040-01 | ORD-1140 | tech pack freeze | 2026-06-03 | 2026-06-03 | 0 | Done | No
TNA-040-02 | ORD-1140 | BOM final approval | 2026-06-06 | 2026-06-08 | 2 | Delayed | No
TNA-040-03 | ORD-1140 | fabric booking | 2026-06-08 | 2026-06-08 | 0 | Done | No
TNA-040-04 | ORD-1140 | trim booking | 2026-06-10 | 2026-06-13 | 3 | Delayed | No
TNA-040-05 | ORD-1140 | fit sample sent | 2026-06-14 |  |  | Open | No
TNA-040-06 | ORD-1140 | fit approval | 2026-06-20 | 2026-06-23 | 3 | Delayed | No
TNA-040-07 | ORD-1140 | size set sample | 2026-06-24 | 2026-06-23 | -1 | Done | No
TNA-040-08 | ORD-1140 | PP sample approval | 2026-06-30 |  |  | Open | Yes
TNA-040-09 | ORD-1140 | fabric in-house | 2026-07-02 |  |  | Open | Yes
TNA-040-10 | ORD-1140 | bulk cutting start | 2026-07-04 | 2026-07-06 | 2 | Delayed | Yes
TNA-040-11 | ORD-1140 | sewing start | 2026-07-07 | 2026-07-12 | 5 | Delayed | Yes
TNA-040-12 | ORD-1140 | inline QC | 2026-07-11 | 2026-07-10 | -1 | Done | No
TNA-040-13 | ORD-1140 | finishing & pressing | 2026-07-13 |  |  | Open | No
TNA-040-14 | ORD-1140 | final inspection | 2026-07-15 |  |  | Open | Yes
TNA-040-15 | ORD-1140 | packing | 2026-07-16 | 2026-07-21 | 5 | Delayed | No
TNA-040-16 | ORD-1140 | ex-factory | 2026-07-18 | 2026-07-21 | 3 | Delayed | Yes

## risk_register
risk_id | risk_area | description | probability | impact | risk_score | mitigation | owner | linked_sheet | status
RISK-001 | Material | Main fabric arrival after planned cut date | 4 | 5 | 20 | Book greige fabric earlier; create alternate supplier option | Sourcing | MRP_material_requirements | Open
RISK-002 | Capacity | Sewing line overloaded during same delivery week | 3 | 5 | 15 | Rebalance between labs L3/L8; authorize overtime only for critical path | Production | orders / line_capacity | Open
RISK-003 | Quality | PP sample not approved before bulk start | 3 | 4 | 12 | No bulk cutting before PP approval; daily approval tracker | Product Dev | TNA_calendar | Monitoring
RISK-004 | Supplier | High-risk supplier has long payment confirmation cycle | 2 | 4 | 8 | Switch to Net 30 preferred suppliers; pre-approve POs | Merchandising | suppliers | Open
RISK-005 | Data | Tech pack version mismatch between BOM and factory | 3 | 5 | 15 | Freeze version IDs; use one source of truth for style master | Technical Office | style_master | Open
RISK-006 | Sustainability | Claim not backed by certificate at shipment | 2 | 4 | 8 | Attach certificate to material master and PO before launch | Compliance | materials_inventory | Monitoring

## data_dictionary
sheet | field | description | type | logic
orders | order_id | Unique production order identifier | Text | Required
orders | planned_smv | Standard minutes per garment pulled from style master | Formula | VLOOKUP from style_master
orders | capacity_days_needed | Total standard minutes divided by assigned line daily available minutes | Formula | Uses line_capacity
product_matrix | avg_time_minutes | Average operation time in minutes | Number | Based on SMV/SAM logic
line_capacity | available_smv_minutes_day | Net daily minutes adjusted by efficiency and uptime | Formula | Operators × shift hours × 60 × efficiency × uptime
BOM | usage_qty_per_garment | Component consumption per garment | Number | Per style/component
MRP_material_requirements | purchase_needed_qty | Required qty minus available material stock | Formula | MAX(0, requirement-stock)
TNA_calendar | delay_days | Actual date minus planned date | Formula | Blank if actual date missing
phase_capacity | bottleneck_flag | Flags phases with low available minutes | Formula | Threshold based